## Indicative 2022 APP
Republic of the Philippines
Department of Education
Region III
Schools Division of Angeles City
Indicative Annual Procurement Plan for FY 2022
Code (PAP) | Procurement Program/ Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (Brief description of Program/Project)
|  |  |  | Ads/ Post of IB/REI | Sub/ Open of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO
A. FURNITURES & EQUIPMENTS
| Office Equipments | OSDS, CID SGOD | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 1074000 | Various Equipments
| ICT Equipment | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 400000 | Various Equipments
| Furniture & Fixture | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 300000 | Various Equipments
| Office Equipments | Elementary | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 12328000 | Various Equipments
| ICT Equipment | Elementary | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 7120000 | Various Equipments
| Furniture & Fixture | Elementary | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 19100000 | Various Equipments
B. REPAIR OF SCHOOL BUILDINGS
N/A
C. PROFESSIONAL SERVICES
| Janitorial Manpower Services | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  |  | 222000 | Professional Services
| Security Manpower Services | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  |  | 360000 | Professional Services
| Job Order | OSDS | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  |  | 1134000 | Professional Services
D. SUPPLIES AND MATERIALS
| Common use supplies and materials available at the Procurement Office | OSDS, CID SGOD | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 842414.208 |  | Procurement Service
| Supplies and Materials not available at the Procurement Service | OSDS, CID SGOD | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 82300 |  | Outside Suppliers
| Printing materials (Duplicator ink and Master) | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 80000 |  | Replacement of parts/Replenishment of consumables
| Photocopier Ink & Parts | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 100000 |  | Replacement of parts/Replenishment of consumables
| Tires / Automotive batt. | OSDS, CID SGOD | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 35000 |  | Replacement of tires or Automotive Battery
E. UTILITIES
| Water Services | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 150000 |  | Angeles City Water District
| Electricity Services | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 1395000 |  | Angeles Electric Corporation
F. COMMUNICATION
| Telephone and Internet Connection | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 1032000 |  | Datelcom, Globe, Converge
G. REPAIR AND MAINTENANCE
| Repair of Office Facilities | OSDS, CID, SGOD | Small Value Procurement | N/A | N/A | N/A | N/A | GoP |  | 600000 |  | Various Office Facilities Repair
| Motor Vehicle | OSDS, CID, SGOD | Shopping | N/A | N/A | N/A | N/A | GoP |  | 48000 |  | Preventive Maintenance for Motor Vehicles
| Air Conditioners | OSDS, CID, SGOD | Shopping | N/A | N/A | N/A | N/A | GoP |  | 120000 |  | Cleaning and Preventive Maintenance of Airconditioners
| Gasoline Consumption | OSDS, CID, SGOD |  | N/A | N/A | N/A | N/A | GoP |  | 96000
H. TRAININGS/SEMINARS
| Division Trainings - Division MOOE INSET Funds | OSDS, CID SGOD, School Heads Teachers | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 2120000 |  | Various Trainings in the Division Office
I. MODULES/LAS
| Early Procurement Activities for the Development and Production of Self- Learning Modules (3rd and 4th Quarter FY2021) | DepEd Angeles City Public School | Competitive Bidding | 2021-12-14 | 2022-01-04 | Short of Award
| Early Procurement Activities for the Development and Production of Self- Learning Modules FY2022 | DepEd Angeles City Public School | Competitive Bidding | 2022-02-07 | 2022-02-22 | Short of Award
| Prepared by: |  |  | Recommending approval: |  |  |  |  | Approved:
| MARIA CRISTINA S. SARMIENTO |  |  | FERNANDINA P. OTCHENGCO, PHD CESE |  |  |  |  | MA. IRELYN P. TAMAYO, PhD CESE
| BAC Secretariat |  |  | BAC Chair |  |  |  |  | Head of Procuring Entity

## ADDITIONAL REPAIR (hidden)
REPUBLIC OF THE PHILIPPINES | REPUBLIC OF THE PHILIPPINES
DEPARTMENT OF EDUCATION | DEPARTMENT OF EDUCATION
CY 2021 BASIC EDUCATIONAL FACILITIES FUND | STATUS REPORT OF CY 2021 BASIC EDUCATIONAL FACILITIES FUND | [9 empty] | ANNEX B
REPAIR OF CLASSROOMS | REPAIR OF CLASSROOMS
PROJECT ID | REGION | DIVISION | SCHOOL ID | SCHOOL NAME | MUNICIPALITY | LD | TOTAL NO. OF SITES | TOTAL PHYSICAL TARGET | TOTAL NO. OF TOILETS | ALLOCATION | SCOPE OF WORK | PRE-PROCUREMENT MEETING | PREPARATION OF BIDDING DOCUMENTS | ADVERTISEMENT/POSTING OF INVITATION TO BID | ISSUANCE AND AVAILABILITY OF BIDDING DOCUMENTS | PRE-BID CONFERENCE | REQUEST FOR CLARIFICATION | SUPPLEMENTAL/BID BULLETINS | SUBMISSION AND RECEIPT OF BIDS | OPENING OF BIDS AND ELIGIBILITY CHECK BID EVALUATION | POST QUALIFICATION | PREPARATION AND APPROVAL OF RESOLUTION TO AWARD | ISSUANCE OF NOTICE OF AWARD | CONTRACT PREPARATION AND SIGNING | PERFECTION AND APPROVAL OF CONTRACT | ISSUANCE OF NTP | START DATE | CALENDAR DAYS | TARGET DATE | COST OF APPROVED BUDGET | CONTRACTOR | % ACCOMPLISHMENT | REMARKS
REPAIR 2021- RIII- ANGELES CITY- 013 | Region III | Angeles City |  | Angeles City National Trade School | ANGELES CITY | 1 | 1 | 16 |  | 3116479.76 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 120 | November 29, 2021 | 3111464.79 | RAS2 CONSTRUCTION | 85% | ON GOING
REPAIR 2021- RIII- ANGELES CITY- 013 | Region III | Angeles City |  | Francisco G. Nepomuceno Memorial High School | ANGELES CITY | 1 | 1 | 24 |  | 2923827.98 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 2916984.81 | EB MATIAS CONSTRUCTION AND TRADING | 100% | COMPLETED
REPAIR 2021- RIII- ANGELES CITY- 013 | Region III | Angeles City |  | Rafael L. Lazatin MHS | ANGELES CITY | 1 | 1 | 12 |  | 2515459.64 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 2509960.73 | TG OCAMPO CONSTRUCTION AND SURVEYING SERVICES | 100% | COMPLETED
REPAIR 2021- RIII- ANGELES CITY- 013 | Region III | Angeles City |  | Angeles City National High School | ANGELES CITY | 1 | 1 | 32 |  | 7096381.72 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 120 | November 29, 2021 | 7086139.77 | GMO CONSTRUCTION | 80% | ON GOING
REPAIR 2021- RIII- ANGELES CITY- 013 | Region III | Angeles City |  | Cutud ES | ANGELES CITY | 1 | 1 | 3 |  | 1350000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 1344133.09 | MAM CONSTRUCTION AND TRADING | 80% | ON GOING
REPAIR 2021- RIII- ANGELES CITY- 003 | Region III | Angeles City |  | Northville 15 IS | ANGELES CITY | 1 | 1 | 2 |  | 900000 | Repair of Classrooms | June 4, 2021 | June 19, 2021 | June 20, 2021 | July 21, 2021 to July 26, 2021 |  |  |  | July 30, 2021 | July 30, 2021 | July 30, 2021 | August 2, 2021 | August 6, 2021 | August 9, 2021 | August 16, 2021 | August 17, 2021 | August 24, 2021 | 60 | October 21, 2021 | 892888.88 | TRACCOR BUILDERS | 70% | ON GOING
REPAIR 2021- RIII- ANGELES CITY- 011 | Region III | Angeles City |  | Epza Rest ES | ANGELES CITY | 1 | 1 | 4 |  | 1800000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 1794988.33 | NULAS BUILDERS | 90% | ON GOING
REPAIR 2021- RIII- ANGELES CITY- 007 | Region III | Angeles City |  | Pulung Bulu ES | ANGELES CITY | 1 | 1 | 2 |  | 900000 | Repair of Classrooms | June 4, 2021 | June 19, 2021 | June 20, 2021 | July 21, 2021 to July 26, 2021 |  |  |  | July 30, 2021 | July 30, 2021 | July 30, 2021 | August 2, 2021 | August 6, 2021 | August 9, 2021 | August 16, 2021 | August 17, 2021 | August 24, 2021 | 60 | October 21, 2021 | 892888.88 | TRACCOR BUILDERS | 50% | ON GOING
| Region III | Angeles City |  | Sto. Domingo IS | ANGELES CITY | 1 | 1 | 6 |  | 2700000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 2689371.37 | PVB CONSTRUCTION AND TRADING | 80% | ON GOING
| Region III | Angeles City |  | Leoncia Village ES | ANGELES CITY | 1 | 1 | 2 |  |  | Repair of Classrooms | June 4, 2021 | [19 empty] | 50% | ON GOING
| Region III | Angeles City |  | Apung Guidang ES | ANGELES CITY | 1 | 1 | 1 |  | 500000 | Repair of Classrooms | June 4, 2021 | June 19, 2021 | June 20, 2021 | July 21, 2021 to July 26, 2021 |  |  |  | July 30, 2021 | July 30, 2021 | July 30, 2021 | August 2, 2021 | August 6, 2021 | August 9, 2021 | August 16, 2021 | August 17, 2021 | August 24, 2021 | 60 | October 21, 2021 | 494888.88 | TRACCOR BUILDERS | 80% | ON GOING
| Region III | Angeles City |  | Angeles ES | ANGELES CITY | 1 | 1 | 8 |  | 3600000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 120 | November 29, 2021 | 3593489.6 | ELDICO BUILDERS | 80% | ON GOING
| Region III | Angeles City |  | Sta. Teresita ES | ANGELES CITY | 1 | 1 | 11 |  | 4950000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 120 | November 29, 2021 | 4938888.88 | TRACCOR BUILDERS | 70% | ON GOING
| Region III | Angeles City |  | Pampang ES | ANGELES CITY | 1 | 1 | 5 |  | 2250000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 2245474.37 | GMO CONSTRUCTION | 80% | ON GOING
| Region III | Angeles City |  | Sapalibutad ES | ANGELES CITY | 1 | 1 | 3 |  | 1350000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 1344568.33 | APU CONSTRUCTION INCORPORATION | 90% | ON GOING
| Region III | Angeles City |  | Pulung Cacutud ES | ANGELES CITY | 1 | 1 | 2 |  | 900000 | Repair of Classrooms | June 4, 2021 | June 19, 2021 | June 20, 2021 | July 21, 2021 to July 26, 2021 |  |  |  | July 30, 2021 | July 30, 2021 | July 30, 2021 | August 2, 2021 | August 6, 2021 | August 9, 2021 | August 16, 2021 | August 17, 2021 | August 24, 2021 | 60 | October 21, 2021 | 892888.88 | TRACCOR BUILDERS | 50% | ON GOING
| Region III | Angeles City |  | Salapungan ES | ANGELES CITY | 1 | 1 | 3 |  | 1350000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 1345777.5 | ALTITUDE ENGINEERING AND CONSTRUCTION | 100% | COMPLETED
| Region III | Angeles City |  | San Ignacio ES | ANGELES CITY | 1 | 1 | 4 |  | 1800000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 1794767.82 | V. TRILLANA BUILDERS AND TRADING | 100% | COMPLETED
| Region III | Angeles City |  | Belen Homesite ES | ANGELES CITY | 1 | 1 | 3 |  | 1350000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 1344960.94 | RAS2 CONSTRUCTION | 90% | ON GOING
| Region III | Angeles City |  | Air Force ES | ANGELES CITY | 1 | 1 | 3 |  | 1350000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 1344973.74 | RAS2 CONSTRUCTION | 90% | ON GOING
| Region III | Angeles City |  | Gueco Balibago ES | ANGELES CITY | 1 | 1 | 5 |  | 2250000 | Repair of Classrooms | June 4, 2021 | June 11, 2021 | June 14, 2021 | June 15, 2021 to June 22, 2021 | June 22, 2021 | June 23, 2021 | June 24, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 12, 2021 | July 14, 2021 | July 23, 2021 | July 27, 2021 | August 2, 2021 | 90 | October 30, 2021 | 2244540.91 | MARVERIC BUILDERS | 80% | ON GOING
[8 empty] | 151 |  | 44952149.1 | [19 empty] | 44824040.5
[8 empty] | 144 |  | 41752149.1 | [19 empty] | 41650484.98
7000000

## Procurement Status 2021 (hidden)
| SARO NO. | DATE OF SARO | TITLE | ALLOTMENT |  | MODE OF PROCUREMENT | PRE-PROCUREMENT | PRE-BID CONFERENCE | BID OPENING | CONTRACTOR | BID AMOUNT | RTA | NOA | CONTRACT | NTP | DELIVERY | SAVINGS | UTILIZATION | DISBURSEMENT | BALANCE
1 | DEPED-ROIII-2021-03-055 | MARCH 1, 2021 | PRINTING SERVICES FOR THE PROVISION OF EPP, TLE & SENIOR LEARNING RECOURCES FOR QUARTERS 3 & 4 OF SY 2020-2021 | 6149329 |  | COMPETITIVE BIDDING | MARCH 17, 2021 | MARCH 26, 2021 | APRIL 12, 2021 | CRISMAN PRINTING SERVICES | 4796476.62 | [5 empty] | 1352852.38 | 4796476.62 | 0 | 1352852.38 | savings procured
2 | DEPED-ROIII-2021-02-026 | FEBRUARY 10, 2021 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR KINDER TO GRADE 3 LEARNERS FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 | 6051427.26 |  | COMPETITIVE BIDDING | MARCH 18, 2021 | MARCH 30, 2021 | APRIL 13, 2021 | FORGEMS MARKETING COMPANY INC. | 3624788.6 | [5 empty] | 2426638.66 | 3624788.6 | 0 | 2426638.66
3 | DEPED-ROIII-2021-03-088 | MARCH 8, 2021 | PROCUREMENT OF PRINTERS AND INK FOR THE PROVISION OF LEARNING RESOURCES FOR ARTS, PHYSICAL EDUCATION, ARALING PANLIPUNAN, EDUKASYON PAGPAPAPAKATAO, AND MUSIC FOR QUARTER 3 SY2020-2021 | 1947250 |  | COMPETITIVE BIDDING | MARCH 19, 2021 | MARCH 31, 2021 | APRIL 15, 2021 | GAKKEN PHILIPPINES INC. | 1928722 | [5 empty] | -1928722 | 1928722 | 0 | 18528
5 | DEPED-ROIII-2021-03-146 | MARCH 23, 2021 | PROVISION OF LEARNING RESOURCES FOR GRADE 4 - GRADE 10 3RD QUARTER REQUIREMENTS OF SY 2020-2021 | 962907 |  | SMALL VALUE PROCUREMENT/NEGOTIATED PROCUREMENT | N/A | N/A | APRIL 27, 2021 | MGD PRINTING | 770325.6 |  | FOR REPEAT ORDER |  |  |  | 192581.4 | 0 | 0 | 192581.4
6 | OSEC-3-20-2816 | DECEMBER 22, 2020 | RELEASE OF ADDITIONAL MOOE FOR SCHOOL DIVISION OFFICEof (SDO) 1,000,000 |  |  | 501,000.00 (RFQ for anti covid equipment) | N/A | N/A
7 | DEPED-ROIII-2021-03-055 | MARCH 1, 2021 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 -BATCH 2 |  | 2788959.07 | COMPETITIVE BIDDING | APRIL 23, 2021 | MAY 11, 2021 | MAY 24, 2021 | NED ARNNIE ENTERPRISES | 2765679 |  | FOR REPEAT ORDER |  |  |  | -2765679
9 | DEPED-ROIII-2021-02-026 | FEBRUARY 10, 2021 | PROCUREMENT OF LONG BONDPAPERS FOR THE PROVISION OF LEARNING RESOURCES FOR QUARTER 3 SY2020-2021 - BATCH 2 |  | 1009060 | COMPETITIVE BIDDING | N/A | JULY 1, 2021 | JULY 6, 2021 | NED ARNNIE ENTERPRISES | 1009018 |  | DELIVERED
10 | DEPED-ROIII-2021-05-298 | MAY 4, 2021 | PROCUREMENT OF A4 SIZE BOND PAPERS FOR THE IMPLEMENTATION OF BE-LCP PROVISION OF LEARNING RESOURCES AS PER JOINT MEMORANDUM DM-OUCI-2021-107 DATED APRIL 12, 2021 | 1002765 |  | COMPETITIVE BIDDING | N/A | JUNE 3, 2021 | JUNE 16, 2021 | TRIPLEX ENTERPRISES | 732, 294.00 |  | DELIVERED |  |  |  | 270471
11 | DEPED-ROIII-2021-05-318 | MAY 4, 2021 | PROCUREMENT OF LONG BOND PAPERS FOR THE IMPLEMENTATION OF BE-LCP PROVISION OF LEARNING RESOURCES AS PER JOINT MEMORANDUM DM-OUCI-2021-098 DATED APRIL 16, 2021 | 1412287 |  | COMPETITIVE BIDDING | N/A | JUNE 3, 2021 | JUNE 16, 2021 | NED ARNNIE ENTERPRISES | 1388742 |  | DELIVERED |  |  |  | 23545
12 |  |  | Procurement of Network Infrastructure to Division Office to Support DepEd Enterprise Resource Planning System | 1000000 |  | COMPETITIVE BIDDING |  |  | September 7, 2021 | HYPERNET-INTERNET & BUSINESS SOLUTIONS, INC. | 940000 |  | DELIVERED
|  |  | Procurement of Ubiquiti Switches Network Infrastructure to Division Office to Support DepEd Enterprise Resource Planning System |  | 60000 | CONTIGUOUS PROCUREMENT | N/A | N/A | N/A | HYPERNET-INTERNET & BUSINESS SOLUTIONS, INC. | 60000 |  | DELIVERED
13 | DEPED-ROIII-2021-07-1428 | JULY 2, 2021 | Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | 6911464 |  | COMPETITIVE BIDDING | August 6, 2021 | August 18, 2021 | August 31, 2021 | Roman Instructional Media Resources, Inc | P 4,892,572.00 |  | DELIVERED
14 | DEPED-ROIII-2021-08-1492 | AUGUST 16, 2021 | Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | 11133714 |  | COMPETITIVE BIDDING | August 27, 2021 | September 9, 2021 | September 21, 2021 | FAYE AND SAM GENERAL MERCHANDISE | 7, 562, 043.00 |  | DELIVERED
16 |  | AUGUST 16, 2021 | Procurement of Long Bond Papers for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (18,798 reams) |  | 3571671 | COMPETITIVE BIDDING | November 16, 2021 | November 25, 2021 | November. 29, 2021 | NAPPCO | 2488859.2
16 | DEPED-ROIII-2021-07-1428 | JULY 2, 2021 | Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (8075 pcs) | 2018892 |  | COMPETITIVE BIDDING | September 14, 2021 | September 28, 2021 | October 12, 2021 | FAYE AND SAM GENERAL MERCHANDISE | P 1, 287,962.50
|  |  | School Based Feeding Program |  |  |  | Failed Bidding |  | September 28, 2021
Failed Bidding
Negotiated Bidding
17 | SUB-ARO Order No. DEPED-ROIII-2021-09-2030 | AUGUST 27, 2021 | Purchase of SPED Equipment and Materials for SPED Inclusive Learning Resource Center (ILRC) | 2000000 |  | COMPETITIVE BIDDING |  |  |  | PROVERBS ENTERPRISES
18 |  |  | TVL | 2160791 |  | COMPETITIVE BIDDING |  |  |  | FAYE AND SAM GENERAL MERCHANDISE | 2, 017,285.00

## 2021 APP (hidden)
Department of Education
Region III
DIVISION OF CITY SCHOOLS
Angeles City
Jesus Street, Pulungbulu, Angeles City
Tel. No. (045) 322-4106; 322-4101; 322-4702 / Fax Nos. (045) 887-6099
DepEd Angeles City Annual Procurement Plan for FY 2021
Code (PAP) | Procurement Program/ Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (Brief description of Program/Project)
|  |  |  | Ads/ Post of IB/REI | Sub/ Open of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO
A. FURNITURES & EQUIPMENTS
| Office Equipments | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP
| ICT Equipment | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP
| Furniture & Fixture | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP
| Office Equipments | Elementary | Shopping | N/A | N/A | N/A | N/A | GoP
| ICT Equipment | Elementary | Shopping | N/A | N/A | N/A | N/A | GoP
| Furniture & Fixture | Elementary | Shopping | N/A | N/A | N/A | N/A | GoP
B. REPAIR OF SCHOOL BUILDINGS
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT ABELARDO G. TINIO ES | Elementary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 2631461.32
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT CUTUD ES | Elementary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 1445760.8
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT EPZA RESETTLEMENT ES | Elementary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 1972580.7
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT GUECO BALIBAGO ES | Elementary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 1302198.99
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT SAPANGBATO ES | Elementary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 1822630.86
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT DON PEPE HENSON MEMORIAL ES | Elementary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 2251616.96
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT LOURDES NORTHWEST ES | Elementary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 2453929.34
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT NORTHVILLE 15 IS | Elementary/Secondary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 8148888.88
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT ANGELES CITY NHS | Secondary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 3586937.95
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT DR. CLEMENTE N. DAYRIT SR. MEMORIAL HS | Secondary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 2926602.27
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT ANGELES CITY SCIENCE HS | Secondary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 3968551.44
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT GOV. RAFAEL. L. LAZATIN IS | Elementary/Secondary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 3353333.09
| CY 2020 BEFF BATCH 2 REPAIR OF CLASSROOM SCHOOL BUILDINGS AT AMSIC IS | Elementary/Secondary | Public Bidding | 2020-09-04 | 2020-09-22 | 2020-11-17 | 2020-11-19 | GoP |  |  | 5503321.77
| CY2020 BEFF Batch 2 Repair of Classrooms at Pineda Gutierrez ES | Elementary | SVP | 2020-10-01 | 2020-10-07 | 2020-11-20 | 2020-11-24 | GoP |  |  | 701888.88
| CY2020 BEFF Batch 2 Repair of Classrooms at Pampang Elementary School | Elementary | SVP | 2020-10-01 | 2020-10-07 | 2020-11-20 | 2020-11-24 | GoP |  |  | 698888.88
| CY2020 BEFF Batch 2 Repair of Classrooms at Air Force City Elementary School | Elementary | SVP | 2020-10-01 | 2020-10-07 | 2020-11-20 | 2020-11-24 | GoP |  |  | 698888.88
C. PROFESSIONAL SERVICES | `
| Janitorial Manpower Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 216000
| Security Manpower Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A |  |  | 288000
| Job Order | OSDS, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 854087.82
D. SUPPLIES AND MATERIALS
| Common use supplies and materials available at the Procurement Office | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 697797.15 |  | Procurement Service
| Supplies and Materials not available at the Procurement Service | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 143054 |  | Outside Suppliers
| Printing materials (RISO ink and Riso Master) | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 100000 |  | UBIX COR./ HP
| Photocopier Ink & Parts | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 120000 |  | UBIX CORP.
| Tires / Automotive batt. | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 35000 |  | Outside Suppliers
E. UTILITIES
| Water Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 240000 |  | Angeles City Water District
| Electricity Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 1300000 |  | Angeles Electric Corporation
F. COMMUNICATION
| Telephone and Internet Connection | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 290000 |  | Datelcom, Globe, Converge
G. REPAIR AND MAINTENANCE
| Motor Vehicle | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP |  | 150000 |  | Preventive Maintenance for Motor Vehicles
| Air Conditioners | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP |  | 100000 |  | Cleaning and Preventive Maintenance of Airconditioners
| Gasoline Consumption | OSDS, CID SGOD, | [5 empty] | GoP
H. TRAININGS/SEMINARS
| Division Trainings/ HRTD | OSDS, CID SGOD, School Heads Teachers | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 5300000 | Various Trainings in the Division Office
I. MODULES/LAS
| Basic Education Learning Continuity Plan-Provision of Learning Resources Lot 1 | CID, School Heads Teachers | Public Bidding | 2020-09-07 | 2020-09-28 | 2020-10-06 | 2020-10-08 | GoP |  |  | 5588888.88
| Basic Education Learning Continuity Plan-Provision of Learning Resources Lot 2 | CID, School Heads Teachers | Public Bidding | 2020-09-07 | 2020-09-28 | 2020-10-06 | 2020-10-08 | GoP |  |  | 5588888.88
| Basic Education Learning Continuity Plan-Provision of Learning Resources Lot 3 | CID, School Heads Teachers | Public Bidding | 2020-09-07 | 2020-09-28 | 2020-10-06 | 2020-10-08 | GoP |  |  | 5718888.88
| Basic Education Learning Continuity Plan-Provision of Learning Resources Lot 4 | CID, School Heads Teachers | Public Bidding | 2020-09-07 | 2020-09-28 | 2020-10-06 | 2020-10-08 | GoP |  |  | 4288888.88
| Batch 2- Basic Education Learning Continuity Plan-Provision of Learning Resources | CID, School Heads Teachers | Public Bidding | 2020-11-06 | 2020-11-23 | 2020-11-25 | 2020-11-26 | GoP |  |  | 4406400
| Batch 3- Basic Education Learning Continuity Plan-Provision of Learning Resources | CID, School Heads Teachers | Public Bidding | 2020-12-12 | 2020-12-21 | 2020-12-22 | 2020-12-28 | GoP |  |  | 1013472
| Batch 4- Basic Education Learning Continuity Plan-Provision of Learning Resources | CID, School Heads Teachers | Public Bidding | 2020-12-12 | 2020-12-21 | 2020-12-22 | 2020-12-28 | GoP |  |  | 3687414.15
[8 empty] | Total: |  | 4533938.97 | 69953036.54
DEFINITION | [9 empty] | Remarks
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions. | [8 empty] | Programs and projects should be alligned with budget documents, and especially those posted at the PhilGeps.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (pre-procurement conference; advertising/posting; pre-bid conference; eligibility screening; submission and receipt of bids; bid evalutaion; post qualification; award of contract; contract preparation), delivery/completion and acceptance/turnover.
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund | [8 empty] | Breakdwon into MOOE and
7. Estimated Budget - Agency approved estimate of project/program costs | [8 empty] | any remark that will help
8. Remarks - brief description of program or project | [8 empty] | GPPB track programs and
projects.
| Prepared by: |  |  | Recommending approval: |  |  |  |  | Approved:
| MARIA CRISTINA S. SARMIENTO |  |  | LYN V. LANSANGAN |  |  |  |  | MA. IRELYN P. TAMAYO, PhD CESE
| Project Development Officer I |  |  | Chief Education Supervisor-SGOD |  |  |  |  | Schools Division Superintendent

## 2020 APP (hidden)
Department of Education
Region III
DIVISION OF CITY SCHOOLS
Angeles City
Jesus Street, Pulungbulu, Angeles City
Tel. No. (045) 322-4106; 322-4101; 322-4702 / Fax Nos. (045) 887-6099
DepEd Angeles City Annual Procurement Plan for FY 2020
Code (PAP) | Procurement Program/ Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (Brief description of Program/Project)
|  |  |  | Ads/ Post of IB/REI | Sub/ Open of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO
A. FURNITURES & EQUIPMENTS
| Office Equipments | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP |  |  | 56428
| ICT Equipment | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP
| Furniture & Fixture | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP
| Office Equipments | Elementary | Shopping | N/A | N/A | N/A | N/A | GoP |  |  | 325500
| ICT Equipment | Elementary | Shopping | N/A | N/A | N/A | N/A | GoP
| Furniture & Fixture | Elementary | Shopping | N/A | N/A | N/A | N/A | GoP
B. REPAIR OF SCHOOL BUILDINGS
|  | ELEM./ SECONDARY | Public Bidding |  |  |  |  | GoP |  |  | 15000000
C. PROFESSIONAL SERVICES
| Janitorial Manpower Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 216000
| Security Manpower Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A |  |  | 273000
| Job Order | OSDS, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 1247148
D. SUPPLIES AND MATERIALS
| Common use supplies and materials available at the Procurement Office | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 1203654.9 |  | Procurement Service
| Supplies and Materials not available at the Procurement Service | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 247808 |  | Outside Suppliers
| Printing materials (RISO ink and Riso Master) | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 100000 |  | UBIX COR./ HP
| Photocopier Ink & Parts | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 120000 |  | UBIX CORP.
| Tires / Automotive batt. | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 35000 |  | Outside Suppliers
E. UTILITIES
| Water Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 198000 |  | Angeles City Water District
| Electricity Services | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 1740000 |  | Angeles Electric Corporation
F. COMMUNICATION
| Telephone and Internet Connection | OSDS, CID SGOD, | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 307200 |  | Datelcom, Globe, Converge
G. REPAIR AND MAINTENANCE
| Motor Vehicle | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP |  | 300000 |  | Preventive Maintenance for Motor Vehicles
| Air Conditioners | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP |  | 100000 |  | Cleaning and Preventive Maintenance of Airconditioners
H. TRAININGS/SEMINARS
| Division Trainings/ HRTD | OSDS, CID SGOD, School Heads Tachers | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 5300000 | Various Trainings in the Division Office
I. GOODS | BE-LCP BATCH 1-LOT 1 | OSDS, CID SGOD, School Heads Tachers | Public Bidding | [7 empty] | 5588888.88 | Modules/LAS
| BE-LCP BATCH 1-LOT 2 | OSDS, CID SGOD, School Heads Tachers | Public Bidding | [7 empty] | 5588888.88 | Modules/LAS
| BE-LCP BATCH 1-LOT 3 | OSDS, CID SGOD, School Heads Tachers | Public Bidding | [7 empty] | 5718888.88 | Modules/LAS
| BE-LCP BATCH 1-LOT 4 | OSDS, CID SGOD, School Heads Tachers | Public Bidding | [7 empty] | 4288888.88 | Modules/LAS
| BE-LCP BATCH 2 | OSDS, CID SGOD, School Heads Tachers | Public Bidding | [7 empty] | 4406400 | Modules/LAS
| BE-LCP BATCH 3 | OSDS, CID SGOD, School Heads Tachers | Public Bidding | [7 empty] | 1103462 | Modules/LAS
[8 empty] | Total: |  | 6087810.9 | 47377345.52
DEFINITION | [9 empty] | Remarks
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions. | [8 empty] | Programs and projects should be alligned with budget documents, and especially those posted at the PhilGeps.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (pre-procurement conference; advertising/posting; pre-bid conference; eligibility screening; submission and receipt of bids; bid evalutaion; post qualification; award of contract; contract preparation), delivery/completion and acceptance/turnover.
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund | [8 empty] | Breakdwon into MOOE and
7. Estimated Budget - Agency approved estimate of project/program costs | [8 empty] | any remark that will help
8. Remarks - brief description of program or project | [8 empty] | GPPB track programs and
projects.
| Prepared by: |  |  | Recommending approval: |  |  |  |  | Approved:
| MARIA CRISTINA S. SARMIENTO |  |  | LYN V. LANSANGAN, Ed.D |  |  |  |  | MA. IRELYN P. TAMAYO, Ph.D, CESE
| Project Development Officer I |  |  | Chief Education Supervisor-SGOD |  |  |  |  | Schools Division Superintendent

## 2021 APP (2nd Sem)
Republic of the Philippines
Department of Education
Region III
Schools Division of Angeles City
Annual Procurement Plan for FY 2021 - 2nd Sem
Code (PAP) | Procurement Program/ Project | PMO/ End-User | Mode of Procurement | Schedule for Each Procurement Activity |  |  |  | Source of Funds | Estimated Budget (PhP) |  |  | Remarks (Brief description of Program/Project)
|  |  |  | Ads/ Post of IB/REI | Sub/ Open of Bids | Notice of Award | Contract Signing |  | Total | MOOE | CO
A. FURNITURES & EQUIPMENTS
| Office Equipments | OSDS, CID SGOD | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 1749000 | Various Equipments
| ICT Equipment | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  |  | Various Equipments
| Furniture & Fixture | OSDS, CID SGOD, | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  |  | Various Equipments
| Office Equipments | Elementary | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  | 38493000 | Various Equipments
| ICT Equipment | Elementary | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  |  | Various Equipments
| Furniture & Fixture | Elementary | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  |  |  | Various Equipments
B. REPAIR OF SCHOOL BUILDINGS
| CY2021 BEFF Repair of Classrooms at Angeles City National Trade School | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 3111464.79 |  | 3111464.79 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Francisco G. Nepomuceno Memorial High School | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 2916984.81 |  | 2916984.81 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Rafael L. Lazatin MHS | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 2509960.73 |  | 2509960.73 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Angeles City National High School | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 7086139.77 |  | 7086139.77 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Cutud ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 1344133.09 |  | 1344133.09 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Northville 15 IS | DepEd Angeles City Public School | Small Value Procurement | June 20, 2021 | July 30, 2021 | August 6, 2021 | August 9, 2021 | CY2021 BEFF Repair Funds | 892888.88 |  | 892888.88 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms Epza Rest ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 1794988.33 |  | 1794988.33 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms Pulung Bulu ES | DepEd Angeles City Public School | Small Value Procurement | June 20, 2021 | July 30, 2021 | August 6, 2021 | August 9, 2021 | CY2021 BEFF Repair Funds | 892888.88 |  | 892888.88 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms Sto. Domingo IS | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 2689371.37 |  | 2689371.37 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms Apung Guidang ES | DepEd Angeles City Public School | Small Value Procurement | June 20, 2021 | July 30, 2021 | August 6, 2021 | August 9, 2021 | CY2021 BEFF Repair Funds | 494888.88 |  | 494888.88 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Angeles ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 3593489.6 |  | 3593489.6 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms Sta. at Teresita ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 4938888.88 |  | 4938888.88 | Repair and Rehabilitation
| CY2021 BEFF Repair of at ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 2245474.37 |  | 2245474.37 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Sapalibutad ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 1344568.33 |  | 1344568.33 | Repair and Rehabilitation
| CY2021 BEFF Repair of Pulung at Cacutud ES Classrooms | DepEd Angeles City Public School | Small Value Procurement | June 20, 2021 | July 30, 2021 | August 6, 2021 | August 9, 2021 | CY2021 BEFF Repair Funds | 892888.88 |  | 892888.88 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms Salapungan ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 1345777.5 |  | 1345777.5 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at San Ignacio ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 1794767.82 |  | 1794767.82 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Belen Homesite ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 1344960.94 |  | 1344960.94 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Air Force ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 1344973.74 |  | 1344973.74 | Repair and Rehabilitation
| CY2021 BEFF Repair of Classrooms at Gueco Balibago ES | DepEd Angeles City Public School | Competitive Bidding | June 14, 2021 | July 6, 2021 | July 12, 2021 | July 14, 2021 | CY2021 BEFF Repair Funds | 2244540.91 |  | 2244540.91 | Repair and Rehabilitation
C. PROFESSIONAL SERVICES
| Janitorial Manpower Services | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  |  | 222000 | Professional Services
| Security Manpower Services | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  |  | 360000 | Professional Services
| Job Order | OSDS | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  |  | 1134000 | Professional Services
D. SUPPLIES AND MATERIALS
| Common use supplies and materials available at the Procurement Office | OSDS, CID SGOD | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 842414.208 |  | Procurement Service
| Supplies and Materials not available at the Procurement Service | OSDS, CID SGOD | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 82300 |  | Outside Suppliers
| Printing materials (Duplicator ink and Master) | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 80000 |  | Replacement of parts/Replenishment of consumables
| Photocopier Ink & Parts | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 100000 |  | Replacement of parts/Replenishment of consumables
| Tires / Automotive batt. | OSDS, CID SGOD | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 35000 |  | Replacement of tires or Automotive Battery
E. UTILITIES
| Water Services | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 150000 |  | Angeles City Water District
| Electricity Services | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 1395000 |  | Angeles Electric Corporation
F. COMMUNICATION
| Telephone and Internet Connection | OSDS, CID SGOD | Direct Contracting | N/A | N/A | N/A | N/A | GoP |  | 1032000 |  | Datelcom, Globe, Converge
G. REPAIR AND MAINTENANCE
| Repair of Office Facilities | OSDS, CID, SGOD | Small Value Procurement | N/A | N/A | N/A | N/A | GoP |  | 600000 |  | Various Office Facilities Repair
| Motor Vehicle | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP |  | 48000 |  | Preventive Maintenance for Motor Vehicles
| Air Conditioners | OSDS, CID SGOD, | Shopping | N/A | N/A | N/A | N/A | GoP |  | 120000 |  | Cleaning and Preventive Maintenance of Airconditioners
| Gasoline Consumption | OSDS, CID SGOD, | [5 empty] | GoP |  | 96000
H. TRAININGS/SEMINARS
| Division Trainings - Division MOOE INSET Funds | OSDS, CID SGOD, School Heads Teachers | NP - Small Value | N/A | N/A | N/A | N/A | GoP |  | 2120000 |  | Various Trainings in the Division Office
I. MODULES/LAS
| Printing Services for the Provision Of EPP, TLE & Senior Learning Resources For Quarters 3 & 4 Of Sy 2020-2021 | DepEd Angeles City Public School | Competitive Bidding | March 24, 2021 | April 12, 2021 | April 15, 2021 | April 29, 2021 | GoP | 4796476.62 |  | 4796476.62 | For the Implementation of BE-LCOP
| Procurement of Bond Papers for the Provision of Learning Resources for Kinder To Grade 3 Learners for Third and Fourth Quarter Requirements SY 2020-2021 | DepEd Angeles City Public School | Competitive Bidding | March 24, 2021 | April 13, 2021 | April 15, 2021 | April 26, 2021 | GoP | 3624788.6 |  | 3624788.6 | For the Implementation of BE-LCOP
| Procurement of Printers and Ink for the Provision Of Learning Resources for Arts, Physical Education, Araling Panlipunan, Edukasyon Pagpapapakatao, and Music For Quarter 3 SY2020-2021 | DepEd Angeles City Public School | Competitive Bidding | March 24, 2021 | April 15, 2021 | April 19, 2021 | April 26, 2021 | GoP | 1928722 |  | 1928722 | For the Implementation of BE-LCOP
| Procurement of Bond Papers for the Provision Of Learning Resources for Third and Fourth Quarter Requirements SY 2020-2021 -Batch 2 | DepEd Angeles City Public School | Competitive Bidding | April 30, 2021 | May 18, 2021 | May 21, 2021 | May 24, 2021 | GoP | 2765679 |  | 2765679 | For the Implementation of BE-LCOP
| Procurement of Long Bond Papers for the Provision Of Learning Resources For Quarter 3 SY2020-2021 - Batch 2 | DepEd Angeles City Public School | Competitive Bidding | June 23, 2021 | July 13, 2021 | July 16, 2021 | July 26, 2021 | GoP | 1009018 |  | 1009018 | For the Implementation of BE-LCOP
| Procurement of A4 Size Bond Papers for the Implementation of BE-LCP Provision of Learning Resources As Per Joint Memorandum DM-OUCI-2021-107 Dated April 12, 2021 | DepEd Angeles City Public School | Competitive Bidding | June 3, 2021 | July 6, 2021 | July 8, 2021 | July 9, 2021 | GoP | 732, 294.00 |  | 732, 294.00 | For the Implementation of BE-LCOP
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | DepEd Angeles City Public School | Competitive Bidding | August 10, 2021 | August 31, 2021 | September 6, 2021 | September 16, 2021 | GoP | 1388742 |  | 1388742 | For the Implementation of BE-LCOP
| Procurement of Network Infrastructure to Division Office to Support DepEd Enterprise Resource Planning System | DepEd Angeles City Public School | Competitive Bidding | August 16, 2021 | September 7, 2021 | September 13, 2021 | September 24, 2021 | GoP | 940000 |  | 940000 | Network Infrastructure
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG | DepEd Angeles City Public School | Competitive Bidding | August 10, 2021 | August 31, 2021 | September 6, 2021 | September 16, 2021 | GoP | P 4,892,572.00 |  | P 4,892,572.00 | For the Implementation of BE-LCOP
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | DepEd Angeles City Public School | Competitive Bidding | August 10, 2021 | August 31, 2021 | September 6, 2021 | September 16, 2021 | GoP | 7, 562, 043.00 |  | 7, 562, 043.00 | For the Implementation of BE-LCOP
| Procurement of Long Bond Papers for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (18,798 reams) | DepEd Angeles City Public School | Competitive Bidding | November 17, 2021 | November. 29, 2021 | December 3, 2021 | December 10, 2021 | GoP | 2488859.2 |  | 2488859.2 | For the Implementation of BE-LCOP
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (8075 pcs) | DepEd Angeles City Public School | Competitive Bidding | September 20, 2021 | November 16, 2021 | November 17, 2021 | November 19, 2021 | GoP | P 1, 287,962.50 |  | P 1, 287,962.50 | For the Implementation of BE-LCOP
| School Based Feeding Program | DepEd Angeles City Public School | (2 Failed Bidding) Negotiated Bidding | November 4, 2021 | November 12, 2021 | November 18, 2021 | November 22, 2021 | GoP | 12869751.31 |  | 12869751.31 | School Feeding Program
| Purchase of SPED Equipment and Materials for SPED Inclusive Learning Resource Center (ILRC) | DepEd Angeles City Public School | Competitive Bidding | October 25, 2021 | November 16, 2021 | November 19, 2021 | November 22, 2021 | GoP | 1795000 |  | 1795000 | SPED Program
| Procurement of Technical-Vocational-Livelihood (TVL) Learning Tools and Equipment | DepEd Angeles City Public School | Competitive Bidding | November 24, 2021 | December 14, 2021 | December 17, 2021 | January 3, 2022 | GoP | 2,017, 285.00 |  | 2,017, 285.00 | TVL Program
| Early Procurement Activities for the Development and Production of Self- Learning Modules (3rd and 4th Quarter FY2021) | DepEd Angeles City Public School | Competitive Bidding | 2021-12-14 | 2022-01-04 | Short of Award | - | - | - | - | - | -
| Early Procurement Activities for the Development and Production of Self- Learning Modules FY2022 | DepEd Angeles City Public School | Competitive Bidding | 2022-02-07 | 2022-02-22 | Short of Award | - | - | - | - | - | -
| Prepared by: |  |  | Recommending approval: |  |  |  |  | Approved:
| MARIA CRISTINA S. SARMIENTO |  |  | FERNANDINA P. OTCHENGCO, PHD CESE |  |  |  |  | MA. IRELYN P. TAMAYO, PhD CESE
| BAC Secretariat |  |  | BAC Chair |  |  |  |  | Head of Procuring Entity

## pmr 2021
Republic of the Philippines
Department of Education
Region III
Schools Division of Angeles City
| ANNEX A |  | ANNEX B | Procurement Monitoring Report as of January 2022
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
| CY2021 BEFF Repair of Classrooms School | Angeles City National Trade School | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 3116479.76 | 0 | 3116479.76 | 3111464.79 | 0 | 3111464.79 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Francisco G. Nepomuceno Memorial High School | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2923827.98 | 0 | 2923827.98 | 2916984.81 | 0 | 2916984.81 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Rafael L. Lazatin MHS | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2515459.64 | 0 | 2515459.64 | 2509960.73 | 0 | 2509960.73 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Angeles City National High School | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 7096381.72 | 0 | 7096381.72 | 7086139.77 | 0 | 7086139.77 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Cutud ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344133.09 | 0 | 1344133.09 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Northville 15 IS | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 900000 | 0 | 900000 | 892888.88 | 0 | 892888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Epza Rest ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1800000 | 0 | 1800000 | 1794988.33 | 0 | 1794988.33 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Pulung Bulu ES | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 900000 | 0 | 900000 | 892888.88 | 0 | 892888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Sto. Domingo IS | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2700000 | 0 | 2700000 | 2689371.37 | 0 | 2689371.37 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Apung Guidang ES | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 500000 | 0 | 500000 | 494888.88 | 0 | 494888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Angeles ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 3600000 | 0 | 3600000 | 3593489.6 | 0 | 3593489.6 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Sta. Teresita ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | November 29, 2021 | November 29, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 4950000 | 0 | 4950000 | 4938888.88 | 0 | 4938888.88 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Pampang ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2250000 | 0 | 2250000 | 2245474.37 | 0 | 2245474.37 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Sapalibutad ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344568.33 | 0 | 1344568.33 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Pulung Cacutud ES | DepEd Angeles City Public School | Small Value Procurement | June 4, 2021 | July, 2021 | July, 2021 | August 2, 2021 | August 2, 2021 | August 2, 2021 | August 3, 2021 | August 6, 2021 | August 10, 2021 | August 11, 2021 | November 30, 2021 | November 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 900000 | 0 | 900000 | 892888.88 | 0 | 892888.88 | COA and ACPST-CCI | May 28, 2021 | July 26, 2021 | July 26, 2021 | July 26, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Salapungan ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1345777.5 | 0 | 1345777.5 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | San Ignacio ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1800000 | 0 | 1800000 | 1794767.82 | 0 | 1794767.82 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Belen Homesite ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344960.94 | 0 | 1344960.94 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Air Force ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 1350000 | 0 | 1350000 | 1344973.74 | 0 | 1344973.74 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
| CY2021 BEFF Repair of Classrooms School | Gueco Balibago ES | DepEd Angeles City Public School | Competitive Bidding | June 4, 2021 | June 14, 2021 | June 22, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 12, 2021 | July 23, 2021 | July 27, 2021 | October 30, 2021 | October 30, 2021 | BEFF CY 2021 REPAIR OF CLASSROOM | 2250000 | 0 | 2250000 | 2244540.91 | 0 | 2244540.91 | COA and ACPST-CCI | May 28, 2021 | June 29, 2021 | June 29, 2021 | June 29, 2021 | July 1, 2021 | November 23, 2021 | N/A
GOODS
1 | PRINTING SERVICES FOR THE PROVISION OF EPP, TLE & SENIOR LEARNING RECOURCES FOR QUARTERS 3 & 4 OF SY 2020-2021 | DepEd Angeles City |  | Competitive Bidding | March 17, 2021 | March 24, 2021 | March 26, 2021 | April 12, 2021 | April 12, 2021 | April 12, 2021 | April 14, 2021 | April 15, 2021 | April 29, 2021 | May 3, 2021 | May 17 2021 | May 17 2021 | GoP | 6149329 | 0 | 6149329 | 4796476.62 | 0 | 4796476.62 | COA and ACPST-CCI | March 19, 2021 | April 5, 2021 | April 5, 2021 | April 5, 2021 | April 7, 2021 | May 10, 2021 | N/A
2 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR KINDER TO GRADE 3 LEARNERS FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 | DepEd Angeles City |  | Competitive Bidding | March 18, 2021 | March 24, 2021 | March 30, 2021 | April 13, 2021 | April 13, 2021 | April 13, 2021 | April 14, 2021 | April 15, 2021 | April 26, 2021 | May 3, 2021 | May 17 2021 | May 17 2021 | GoP | 6051427.26 | 0 | 6051427.26 | 3624788.6 | 0 | 3624788.6 | COA and ACPST-CCI | March 23, 2021 | April 5, 2021 | April 5, 2021 | April 5, 2021 | April 7, 2021 | May 10, 2021 | N/A
3 | PROCUREMENT OF PRINTERS AND INK FOR THE PROVISION OF LEARNING RESOURCES FOR ARTS, PHYSICAL EDUCATION, ARALING PANLIPUNAN, EDUKASYON PAGPAPAPAKATAO, AND MUSIC FOR QUARTER 3 SY2020-2021 | DepEd Angeles City |  | Competitive Bidding | March 19, 2021 | March 24, 2021 | March 31, 2021 | April 15, 2021 | April 15, 2021 | April 15, 2021 | April 16, 2021 | April 19, 2021 | April 26, 2021 | April 28, 2021 | May 28, 2021 | May 28, 2021 | GoP | 1947250 | 0 | 1947250 | 1928722 | 0 | 1928722 | COA and ACPST-CCI | March 23, 2021 | April 5, 2021 | April 5, 2021 | April 5, 2021 | April 7, 2021 | May 10, 2021 | N/A
5 | PROCUREMENT OF BONDPAPERS FOR THE PROVISION OF LEARNING RECOURCES FOR THIRD AND FOURTH QUARTER REQUIREMENTS SY 2020-2021 -BATCH 2 | DepEd Angeles City |  | Competitive Bidding | April 23, 2021 | April 30, 2021 | May 11, 2021 | May 18, 2021 | May 18, 2021 | May 18, 2021 | May 19, 2021 | May 21, 2021 | May 24, 2021 | May 26, 2021 | June 9, 2021 | June 9, 2021 | GoP | 2788959.07 | 0 | 2788959.07 | 2765679 | 0 | 2765679 | COA and ACPST-CCI | May 4, 2021 | May 11, 2021 | May 11, 2021 | May 11, 2021 | May 11, 2021 | June 2, 2021 | N/A
7 | PROCUREMENT OF LONG BONDPAPERS FOR THE PROVISION OF LEARNING RESOURCES FOR QUARTER 3 SY2020-2021 - BATCH 2 | DepEd Angeles City |  | Competitive Bidding | N/A | June 23, 2021 | July 1, 2021 | July 13, 2021 | July 13, 2021 | July 13, 2021 | July 14, 2021 | July 16, 2021 | July 26, 2021 | July 27, 2021 | August 14, 2021 | August 14, 2021 | GoP | 1009060 | 0 | 6149329 | 1009018 | 0 | 1009018 | COA and ACPST-CCI | June 16, 2021 | June 16, 2021 | June 16, 2021 | June 16, 2021 | June 16, 2021 | August 7, 2021 | N/A
8 | PROCUREMENT OF A4 SIZE BOND PAPERS FOR THE IMPLEMENTATION OF BE-LCP PROVISION OF LEARNING RESOURCES AS PER JOINT MEMORANDUM DM-OUCI-2021-107 DATED APRIL 12, 2021 | DepEd Angeles City |  | Competitive Bidding | N/A | June 3, 2021 | June 10, 2021 | July 6, 2021 | July 6, 2021 | July 6, 2021 | July 7, 2021 | July 8, 2021 | July 9, 2021 | July 12, 2021 | July 27, 2021 | July 27, 2021 | GoP | 1002765 | 0 | 6051427.26 | 732, 294.00 | 0 | 732, 294.00 | COA and ACPST-CCI | June 3, 2021 | June 3, 2021 | June 3, 2021 | June 3, 2021 | June 3, 2021 | July 20, 2021 | N/A
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | DepEd Angeles City |  | Competitive Bidding | August 6, 2021 | August 10, 2021 | August 18, 2021 | August 31, 2021 | August 31, 2021 | August 31, 2021 | September 2, 2021 | September 6, 2021 | September 16, 2021 | September 20, 2021 | October 5, 2021 | October 5, 2021 | GoP | 1412287 | 0 | 1947250 | 1388742 | 0 | 1388742 | COA and ACPST-CCI | August 11, 2021 | August 24, 2021 | August 24, 2021 | August 24, 2021 | August 24, 2021 | September 28, 2021 | N/A
10 | Procurement of Network Infrastructure to Division Office to Support DepEd Enterprise Resource Planning System | DepEd Angeles City |  | Competitive Bidding | August 12, 2021 | August 16, 2021 | August 23, 2021 | September 7, 2021 | September 7, 2021 | September 7, 2021 | September 9, 2021 | September 13, 2021 | September 24, 2021 | September 27, 2021 | November 27, 2021 | November 27, 2021 | GoP | 1000000 | 0 | 962907 | 940000 | 0 | 940000 | COA and ACPST-CCI | August 3, 2021 | August 16, 2021 | August 16, 2021 | August 16, 2021 | August 16, 2021 | November 20, 2021 | N/A
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG | DepEd Angeles City |  | Competitive Bidding | August 6, 2021 | August 10, 2021 | August 18, 2021 | August 31, 2021 | August 31, 2021 | August 31, 2021 | September 2, 2021 | September 6, 2021 | September 16, 2021 | September 20, 2021 | October 5, 2021 | October 5, 2021 | GoP | 6911464 | 0 | 2788959.07 | P 4,892,572.00 | 0 | P 4,892,572.00 | COA and ACPST-CCI | August 2, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | September 28, 2021 | N/A
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. USB-OTG, 32 GB ULTRA DUAL DRIVE M3.0/OTG (18,188 pcs) | DepEd Angeles City |  | Competitive Bidding | August 6, 2021 | August 10, 2021 | August 18, 2021 | August 31, 2021 | August 31, 2021 | August 31, 2021 | September 2, 2021 | September 6, 2021 | September 16, 2021 | September 20, 2021 | October 5, 2021 | October 5, 2021 | GoP | 11133714 | 0 | 1009060 | 7, 562, 043.00 | 0 | 7, 562, 043.00 | COA and ACPST-CCI | August 2, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | August 11, 2021 | September 28, 2021 | N/A
| Procurement of Long Bond Papers for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (18,798 reams) | DepEd Angeles City |  | Competitive Bidding | November 16, 2021 | November 17, 2021 | November. 25, 2021 | November. 29, 2021 | November. 29, 2021 | November 29, 2021 | December 1, 2021 | December 3, 2021 | December 10, 2021 | December 13, 2021 | December 28, 2021 | December 28, 2021 | GoP | 3571671 | 0 | 1002765 | 2488859.2 | 0 | 2488859.2 | COA and ACPST-CCI | November 18, 2021 | November 18, 2021 | November 18, 2021 | November 18, 2021 | November 18, 2021 | December 21, 2021 | N/A
| Procurement of Flash Memory Devices for the Implementation of BE-LCP Provision of Learning Resources for Quarters 1 and 2. (8075 pcs) | DepEd Angeles City |  | Competitive Bidding | September 14, 2021 | September 20, 2021 | September 28, 2021 | November 16, 2021 | November 16, 2021 | November 16, 2021 | November 17, 2021 | November 17, 2021 | November 19, 2021 | November 23, 2021 | December 15, 2021 | December 15, 2021 | GoP | 2018892 | 0 | 1412287 | P 1, 287,962.50 | 0 | P 1, 287,962.50 | COA and ACPST-CCI | September 21, 2021 | November 10, 2021 | November 10, 2021 | November 10, 2021 | November 10, 2021 | December7, 2021 | N/A
| School Based Feeding Program | DepEd Angeles City |  | (2 Failed Bidding) Negotiated Bidding | October 26, 2021 | November 4, 2021 | November 9, 2021 | November 12, 2021 | November 12, 2021 | November 12, 2021 | November 15, 2021 | November 18, 2021 | November 22, 2021 | November 25, 2021 | January 31, 2021 | January 31, 2021 | GoP | 12, 875,760.00 | 0 | 1000000 | 12869751.31 | 0 | 12869751.31 | COA and ACPST-CCI | October 28, 2021 | October 28, 2021 | October 28, 2021 | October 28, 2021 | October 28, 2021 | 2022-01-01 | N/A
| Purchase of SPED Equipment and Materials for SPED Inclusive Learning Resource Center (ILRC) | DepEd Angeles City |  | Competitive Bidding | October 20, 2021 | October 25, 2021 | November 3, 2021 | November 16, 2021 | November 16, 2021 | November 16, 2021 | November 17, 2021 | November 19, 2021 | November 22, 2021 | November 23, 2021 | December 23, 2021 | December 23, 2021 | GoP | 2000000 | 0 | 6911464 | 1795000 | 0 | 1795000 | COA and ACPST-CCI | October 28, 2021 | November 9, 2021 | November 9, 2021 | November 9, 2021 | December 15, 2021 | 2022-01-01 | N/A
| Procurement of Technical-Vocational-Livelihood (TVL) Learning Tools and Equipment | DepEd Angeles City |  | Competitive Bidding | November 22, 2021 | November 24, 2021 | December 2, 2021 | December 14, 2021 | December 14, 2021 | December 14, 2021 | December 15, 2021 | December 17, 2021 | January 3, 2022 | January 10, 2022 | February 15, 2022 | February 15, 2022 | GoP | 2160791 | 0 | 11133714 | 2,017, 285.00 | 0 | 2,017, 285.00 | COA and ACPST-CCI | November 26 2021 | December 7, 2021 | December 7, 2021 | December 7, 2021 | December 7, 2021 | 2022-02-01 | N/A
12, 875,760.00
2000000
2160791
0
|  |  | Prepared by: | Prepared: | [7 empty] | Recommended for Approval by: | [10 empty] | APPROVED:
|  |  | MARIA CRISTINA S. SARMIENTO | MARIA CRISTINA S, SARMIENTO | [7 empty] | FERNANDINA P. OTCHENGCO, PhD CESE | [10 empty] | MA. IRELYN P. TAMAYO, PhD CESE
|  |  | BAC Secretariat | BAC Secretariat | [7 empty] | BAC Chair | [10 empty] | Head of the Procuring Entity