## PMR 2023 1st Sem
CY 2023 SDO ANGELES CITY PROCUREMENT MONITORING REPORT
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
GOODS
1 | Release of Program Support Funds for the Implementation of SY 2023-2024 School-Based Feeding Program (SBFP) which includes Nutritious Food Products, Milk, and Operational Expenses | SDO Angeles City | Competitive Bidding | May 12, 2023 | 2023-06-01 | 2023-06-08 | 2023-06-26 | 2023-06-26 | 2023-06-26 | 2023-07-13 | [5 empty] | GAA |  |  | 17094240 |  |  |  | COA and ACPST-CCI | [6 empty] | On - Going Procurement
2 | Funding requirements for the Allocation of Flexible Learning Options-Learning Resources and the development and production of Self-Learning MOdules (SLMs) for CY 2023 | SDO Angeles City | Competitive Bidding | 2023-06-01 | 2023-06-16 | 2023-06-26 | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-25 | [5 empty] | GAA |  |  | 13252034 |  |  |  | COA and ACPST-CCI | [6 empty] | On - Going Procurement
3 | Funding reqiurements for the Procurement of Learning Tools and Equipment-Technical-Vocational-Livelihood (LTE-TVL) toPublic Senior High School | SDO Angeles City | Competitive Bidding | 2023-07-07 | 2023-07-28 | 2023-08-03 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-16 | [5 empty] | GAA |  |  | 1368893 |  |  |  | COA and ACPST-CCI | [6 empty] | On - Going Procurement
12, 875,760.00
2000000
2160791
0
[11 empty] | Recommended for Approval by: | [10 empty] | APPROVED: |  |  | Approved:
|  |  | MARIA CRISTINA S. SARMIENTO | [7 empty] | FERNANDINA P. OTCHENGCO, PhD CESE | [10 empty] | MA. IRELYN P. TAMAYO, PhD CESE |  |  | RONALDO A. POZON PhD, CESO V
|  |  | BAC Secretariat | [7 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity |  |  | Head of Procuring Entity

## PMR 2023 2ND SEM
Region III
SCHOOLS DIVISION OF ANGELES CITY
FY 2023 DepEd Angeles City Procurement Monitoring Report
Region | RO/SDO NAME | Program Category | Procurement Project (Title) | Lot number | PMO/ End-User | Mode of Procurement | Types of Contract | Procurement Planning (DD/MM/YYYY) | Pre- Procurement Conference (DD/MM/YYYY) | Advertisement/Posting of IB/REI (DD/MM/YYYY) | Pre-Bid Conference (DD/MM/YYYY) | Eligibility Check (DD/MM/YYYY) | Submission/Opening of Bids (DD/MM/YYYY) | Bid Evaluation (DD/MM/YYYY) | Post Qualification (DD/MM/YYYY) | Date of BAC Resolution Recommending Award (DD/MM/YYYY) | Notice of Award (DD/MM/YYYY) | Contract Signing (DD/MM/YYYY) | Notice to Proceed (DD/MM/YYYY) | Source of Funds | Total (ABC) | MOOE (ABC) | CO (ABC) | Final Contract Price | Remarks (brief description for FAILED and CANCELED)
III | SDO ANGELES CITY | Special Education Program | Lot 1 -Pocurement for the Additional Program Support Fund for the Conversion of SPED Center to Inclusive Learning Resource Center for Purchase of Assistive Devices and Equipment for the Service Area of the ILRC | LOT 1 | Angeles ES | Competitive Bidding | Goods | 2022-12-27 | 2023-01-06 | 2023-02-07 | 2023-02-14 | 2023-02-27 | 2023-02-27 | 2023-02-27 | 2023-02-28 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-16 | Sub-Aro | 2800000 | 0 | 2800000 | 1400950 | Completed
III | SDO ANGELES CITY | Special Education Program | Lot 2 - Pocurement for the Additional Program Support Fund for the Conversion of SPED Center to Inclusive Learning Resource Center for Purchase of Assistive Devices and Equipment for the Service Area of the ILRC | LOT 2 | Angeles ES | Competitive Bidding | Goods | 2022-12-27 | 2023-01-06 | 2023-02-07 | 2023-02-14 | 2023-02-27 | 2023-02-27 | 2023-02-27 | 2023-02-27 | 2023-03-06 | 2023-03-07 | 2023-03-08 | 2023-03-16 | Sub-Aro |  | 0 |  | 1350500 | Completed
III | SDO ANGELES CITY | School-Based Feeding Program (SBFP) | Procurement of Goods for the Implementation of SY 2023-2024 School-Based Feeding Program (SBFP) which includes Nutritious Food Products, Milk, and Operational Expenses | LOT 1 | Schools | Competitive Bidding | Goods | 2023-04-25 | 2023-05-02 | 2023-06-01 | 2023-06-08 | 2023-06-26 | 2023-06-26 | 2023-06-26 | 12/07/2023; 04/09/2023; 22/09/2023; 26/09/2023 | 2023-09-26 | 2023-09-27 | 2023-09-28 | 2023-09-29 | Sub-Aro | 17094240 | 0 | 17094240 | 17088541.92 | Completed
III | SDO ANGELES CITY | Flexible Learning Options (ADM/ALS/EiE) | Procurement for the Flexible Learning Options-Learning Resources and the development and production of Self-Learning Modules (SLMs) for CY 2023 | LOT 1 | Schools | Competitive Bidding | Goods | 2023-05-25 | 2023-06-01 | 2023-06-16 | 2023-06-26 | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-25 | 2023-07-23 | 2023-07-24 | 2023-07-25 | 2023-08-01 | Sub-Aro | 13252034 | 0 | 13252034 | 7421139.6 | Completed
III | SDO ANGELES CITY | Flexible Learning Options (ADM/ALS/EiE) | Buffer - Procurement for the Flexible Learning Options-Learning Resources and the development and production of Self-Learning Modules (SLMs) for CY 2023 | LOT 1 | Schools | Competitive Bidding | Goods | 2023-11-08 | 2023-11-15 | 2023-11-17 | 2023-11-23 | 2023-12-07 | 2023-12-07 | 2023-12-07 | 2023-12-11 | 2023-12-14 | 2023-12-15 | 2023-12-18 | 2023-12-20 | Sub-Aro | 5830894.4 | 0 | 5830894.4 | 3731673.6 | Completed
III | SDO ANGELES CITY | Learning Tools and Equipment | Procurement of Learning Tools and Equipment-Technical-Vocational-Livelihood (LTE-TVL) to Public Senior High School | LOT 1 | Schools | Competitive Bidding | Goods | 2023-06-30 | 2023-07-07 | 2023-08-19 | 2023-08-03 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-16 | 2023-10-06 | 2023-10-10 | 2023-10-11 | 2023-10-13 | Sub-Aro | 1368893 | 0 | 1368893 | 1323641 | Completed
III | SDO ANGELES CITY | Computerization Program | Network Infrastracture of School Division offices under FY 2023 DepEd Computerization Program (DCP) | LOT 1 | Divison Office | Competitive Bidding | Infrastructure | 2023-10-02 | 2023-10-05 | 2023-10-17 | 2023-10-25 | 2023-11-06 | 2023-11-06 | 2023-11-06 | 2023-11-07 | 2023-11-13 | 2023-11-14 | 2023-11-15 | 2023-11-20 | Sub-Aro | 1500000 | 0 | 1500000 | 1498870 | Completed
III | SDO ANGELES CITY | General Management and Supervision | Procurement for the Printing of Reading Worksheets for Grades 1 to 3 Learners | LOT 1 | Schools | Competitive Bidding | Goods | 2023-07-01 | 2023-08-07 | 2023-08-19 | 2023-08-30 | 2023-09-18 | 2023-09-18 | 2023-09-18 | 2023-09-21 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | Sub-Aro | 1078937 | 0 | 1078937 | 978000 | Completed
III | SDO ANGELES CITY | General Management and Supervision | Procurement of Printing Materials for the FY2023 Implementation of the National Learning Camp (NLC) and other End of School Year (EOSY) break activities supporting the National Learning Recovery Program (NLRP) | LOT 1 | Schools | Competitive Bidding | Goods | 2023-07-01 | 2023-08-07 | 2023-08-19 | 2023-09-01 | 2023-09-20 | 2023-09-20 | 2023-09-20 | 2023-09-25 | 2023-09-25 | 2023-09-26 | 2023-09-27 | 2023-09-29 | Sub-Aro | 1200000 | 0 | 1200000 | 1199000 | Completed
III | SDO ANGELES CITY | General Management and Supervision | Procurement of Printing Materials for the FY2023 Implementation of the National Learning Camp Assessment (NLCA) | LOT 1 | Schools | Competitive Bidding | Goods | 2023-07-01 | 2023-09-22 | 2023-09-26 | 2023-10-05 | 2023-10-17 | 2023-10-17 | 2023-10-17 | 2023-09-22 | 2023-11-06 | 2023-11-07 | 2023-11-08 | 2023-11-15 | Sub-Aro | 2,322.486.95 | 0 | 2,322.486.95 | 2299950 | Completed
| Prepared | [7 empty] | Recommended for Approval by: | [13 empty] | Approved:
| MARIA CRISTINA S. SARMIENTO | [7 empty] | FERNANDINA P. OTCHENGCO, PhD CESE | [13 empty] | RONALDO A. POZON PhD, CESO V
| BAC Secretariat | [7 empty] | BAC Chairperson | [13 empty] | Head of Procuring Entity