## PMR 2023 1st Sem
CY 2023 SDO ANGELES CITY PROCUREMENT MONITORING REPORT
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
GOODS
1 | Release of Program Support Funds for the Implementation of SY 2023-2024 School-Based Feeding Program (SBFP) which includes Nutritious Food Products, Milk, and Operational Expenses | SDO Angeles City | Competitive Bidding | May 12, 2023 | 2023-06-01 | 2023-06-08 | 2023-06-26 | 2023-06-26 | 2023-06-26 | 2023-07-13 | [5 empty] | GAA |  |  | 17094240 |  |  |  | COA and ACPST-CCI | [6 empty] | On - Going Procurement
2 | Funding requirements for the Allocation of Flexible Learning Options-Learning Resources and the development and production of Self-Learning MOdules (SLMs) for CY 2023 | SDO Angeles City | Competitive Bidding | 2023-06-01 | 2023-06-16 | 2023-06-26 | 2023-07-10 | 2023-07-10 | 2023-07-10 | 2023-07-25 | [5 empty] | GAA |  |  | 13252034 |  |  |  | COA and ACPST-CCI | [6 empty] | On - Going Procurement
3 | Funding reqiurements for the Procurement of Learning Tools and Equipment-Technical-Vocational-Livelihood (LTE-TVL) toPublic Senior High School | SDO Angeles City | Competitive Bidding | 2023-07-07 | 2023-07-28 | 2023-08-03 | 2023-08-15 | 2023-08-15 | 2023-08-15 | 2023-08-16 | [5 empty] | GAA |  |  | 1368893 |  |  |  | COA and ACPST-CCI | [6 empty] | On - Going Procurement
12, 875,760.00
2000000
2160791
0
[11 empty] | Recommended for Approval by: | [10 empty] | APPROVED: |  |  | Approved:
|  |  | MARIA CRISTINA S. SARMIENTO | [7 empty] | FERNANDINA P. OTCHENGCO, PhD CESE | [10 empty] | MA. IRELYN P. TAMAYO, PhD CESE |  |  | RONALDO A. POZON PhD, CESO V
|  |  | BAC Secretariat | [7 empty] | BAC Chairperson | [10 empty] | Head of the Procuring Entity |  |  | Head of Procuring Entity