## SDO Angeles City (hidden)
Major procurement activities implemented in the past
For Government funded contracts please include the information over the past 5 or10 years, depending on information availability
For contracts funded by international financiang institutions, please cover all projects in the past
Procuring entity:
| Package name/Project name | Procurement Category | Contract price (PESO) | Source of fund (Government or International financier) | Date of contract signing | Contract period (months) | Name of contractor/supplier/consultant | Procurement method | No. of Bidders | No. of days from Advertisement to Contract Award | Contract implementation status | Payment status (in case of on-going contract, how many percentage of contract price already paid)
COMPLETED PROCUREMENT ACTIVITIES
| Procurement of Mathematical Learning Resources (Manipulative Materials) | GOODS | 488289 | Government budget | 21/3/2024 | 2 | PHILIPPINE RUN HUI TRADING CORP. | Competitive Bidding | 5 |  | Completed | Completed
| Procurement of SDO Angeles City Milk Feeding 2023-2024 | GOODS | 6465738 | Government budget | 2024-04-02 | 1 | LUZON DAIRY COOPERATIVE | Competitive Bidding | 1 |  | Completed | Completed
| Procurement of Printing Materials In-house printing of identified lacking Self- Learning Modules (SLMs) for Public School LearnersProcurement of Printing Materials (Inks, A3 Papers, C2S Book Cover Papers, Saddle Stitcher) | GOODS | 2093606 | Government budget | 14/6/2024 | 2 | GAKKEN (Philippines), INC | Competitive Bidding | 2 |  | Completed | Completed
| School Based Feeding Program SY 2024-2025 | GOODS | 30760056.25 | Government budget | 2024-07-01 |  | Nueva Ecija Federation of Dairy Carabao Cooperative, M.B. Cajucom General Merchandise, EnMiRi Corporation | Competitive Bidding | 4 |  | On-going | On-going
| Procurement of Project under the CY 2024 BEFF, Repair/Rehabilitation of Classrooms Batch 1 at Northville 15 Integrated School, Brgy. Cutud, Angeles City | REPAIR OF SCHOOL BUILDINGS | 4156888.88 | Government budget |  | 4 | TRACCOR BUILDERS | Competitive Bidding | 7 |  | Completed | Completed
| Reproduction of NLC Teaching and Learning Resources (Private Printer) | GOODS | 2367850.41 | Government budget | 2024-09-09 | 2 | RENALMA CORPORATION | Competitive Bidding | 1 |  | Completed | Completed
| Production and delivery of Grade 1 Mathematics Lesson Exemplars (LEs) and Worksheets (WSs) for School Year 2024-2025 | GOODS | 1388470 | Government budget | 2024-11-04 | 1 | GAKKEN (Philippines), INC | Competitive Bidding | 2 |  | Completed | Completed
| Production and delivery of Kindergarten Lesson Exemplars (LEs) and Worksheets (WSs) for School Year 2024-2025 | [9 empty] | Completed | Completed
| Production of Transition Learning Resources of Grade 4 Lesson Exemplars (LEs) and Worksheets (WSs) for the implementation of MATATAG Curriculum for the School Year 2024-2025 | GOODS | 1543362 | Government budget | 2024-11-04 | 2 | GAKKEN (Philippines), INC | Competitive Bidding | 1 |  | Completed | Completed
| Production of Transition Learning Resources of Grade 7 Lesson Exemplars (LEs) and Worksheets (WSs) for the implementation of MATATAG Curriculum for the School Year 2024-2025 | [6 empty] | Competitive Bidding | 1
| Procurement of Materials for the Printing/Production of Grade 1 Transition Learning Resources Lesson Exemplars (LEs) and Worksheets (WSs) for the implementation of the MATATAG Curriculum for SY 2024-2025 | GOODS | 3157738 | Government budget | 2024-11-04 | 2 | GAKKEN (Philippines), INC | Competitive Bidding | 1 |  | Completed | Completed
| Procurement of remediation packages for reading programs | GOODS | 2749125 | Government budget | 5/11/202 | 2 | LAMPARA PUBLISHING HOUSE, INC. | Competitive Bidding | 1 |  | Completed | Completed
| Procurement of printing and delivery of storybooks for reading programs. | GOODS | 1940873.85 | Government budget | 2024-12-17 | 2 | RENALMA CORPORATION | Competitive Bidding | 1 |  | On-going | On-going
| Procurement of Assistive Devices, Equipment, Supplies and Materials for Inclusive Learning Resources Center (ILRC) | GOODS | 7838089.82 | Government budget | 2024-12-13 | 2 | FAYE AND SAM GENERAL MERCHANDISE | Competitive Bidding | 2 |  | On-going | On-going
| Procurement of Learning Tools and Equipment – Technical Vocational Livelihood (LTE-TVL) To Public High School | GOODS | 2099692.666 | Government budget | 2024-10-31 | 2 | PETER JOHN ENTERPRISES | Competitive Bidding | 4 |  | Completed | Completed
| Procurement of Goods for the Implementation of School-Based Feeding Program (SBFP) - Milk Feeding Component for SY 2024-2025 | GOODS | 11941482 | Government budget | 2024-12-16 |  | LUZON DAIRY COOPERATIVE | Competitive Bidding | 2 |  | On-going | On-going

## 2024 PMR (hidden)
Department of Education
Region III
SCHOOLS DIVISION OFFICE OF ANGELES CITY
DepEd Angeles City Supplemental FY 2024 Annual Procurement Plan Non CSE
Code (PAP) | Procurement Program/ Project | PMO/ End-User | Mode of Procurement |  | Schedule for Each Procurement Activity | [8 empty] | Source of Funds | Estimated Budget (PhP) |  |  |  | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Procurement Conference | Ads/ Post of IB/REI | Pre-Bid | Eligibility Check | Sub/ Open of Bids | Bid Evaluation | Post Qualification | Notice of Award | Contract Signing | Notice to Proceed |  | Total | MOOE | CO | CONTRACT AMOUNT
SUPPLIES AND MATERIALS | Procurement of Mathematical Learning Resources (Manipulative Materials) | CID/SDO Angeles City | Competitive Bidding | 2024-02-16 | 20/2/2024 | 2024-02-23 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-07-03 | 2024-11-03 | 21/3/2024 | 2024-03-25 | Sub-Aro | 1032437 | 0 | 1032437 | 488289 | Completed | 488289
SBFP | Procurement of SDO Angeles City Milk Feeding 2023-2024 | SGOD/SDO Angeles City | NP-53.12 Community Participation | 2024-03-01 | 2024-03-08 | 2024-03-10 | 22/3/2024 | 22/3/2024 | 22/3/2024 |  | 2024-04-01 | 2024-04-02 | 2024-04-08 | Sub-Aro | 6562724.07 | 0 | 6562724.07 | 6465738 | Completed | 6465738
TRAININGS/SEMINARS | Procurement of Venue and Board and Lodging for the Conduct of Division Training of Trainers (DTOT) on Matatag Curriculum | SGOD/SDO Angeles City | Competitive Bidding | 2024-04-11 | 2024-04-22 | 2024-05-15 | 2024-06-05 | 2024-05-28 | 2024-06-05 | 2024-05-29 | 2024-06-13 | 2024-06-14 | 2024-06-22 | Sub-Aro | 2380000 | 0 | 2380000 | 2379990 | Completed
SUPPLIES AND MATERIALS | Procurement of Printing Materials In-house printing of identified lacking Self- Learning Modules (SLMs) for Public School LearnersProcurement of Printing Materials (Inks, A3 Papers, C2S Book Cover Papers, Saddle Sticher) | CID/SDO Angeles City | Competitive Bidding | 2024-05-08 | 2024-05-10 | 2024-05-17 | 29/5/2024 | 2024-05-29 | 29/5/2024 | 2024-05-30 | 2024-03-06 | 14/6/2024 | 2024-06-17 | Sub-Aro | 2099220.8 | 0 | 2099220.8 | 2093606 | From Savings/Completed | 2093606
SBFP | School Based Feeding Program SY 2024-2025 | SGOD/SDO Angeles City | Competitive Bidding | 2024-05-10 | 2024-05-17 | 2024-05-24 | 13/06/2024 | 13/06/2024 | 13/06/2024 | 2024-06-26 | 2024-06-28 | 2024-07-01 | 2024-07-09 | Sub-Aro | 34091750 | 0 | 34091750 | 30760056.25 | On-going | 30760056.25
SUPPLIES AND MATERIALS | Savings from Procurement of Mathematical Learning Resources (Manipulative Materials) | CID/SDO Angeles City | NP-53.9 - Small Value Procurement |  | n/a |  | n/a | n/a | n/a |  | 2024-05-29 | n/a | n/a | Sub-Aro | 544131 | 0 | 544131 |  | Completed
REPAIR OF SCHOOL BUILDINGS | Procurement of Project under the CY 2024 BEFF, Repair/Rehabilitation of Classrooms Batch 1 at Northville 15 Integrated School, Brgy. Cutud, Angeles City | SGOD/SDO Angeles City | Competetive Bidding | 2024-05-27 | 2024-06-10 | 2024-06-24 | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-07-09 | Short of Award | 2024-09-18 | 2024-11-04 | Sub-Aro | 4167750.28 | 0 | 4167750.28 | 4156888.88 | Completed | 4156888.88
TRAININGS/SEMINARS | Procurement Meals for the Conduct of School Based Training of Teachers ((K, 1, 4 and 7) on the Matatag Curriculum) | SGOD/SDO Angeles City | Competetive Bidding | 2024-06-05 | 2024-06-06 | 2024-06-13 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | Sub-Aro | 3062500 | 0 | 3062500 |  | Completed
SUPPLIES AND MATERIALS | Reproduction of NLC Teaching and Learning Resources (Private Printer) | CID/SDO Angeles City | Competetive Bidding | 2024-07-23 | 2024-07-25 | 2024-08-02 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-15 | 2024-09-03 | 2024-09-09 | 2024-09-23 | Sub-Aro | 2380000 | 0 | 2380000 | 2367850.41 | 95% Complete | 2367850.41
SUPPLIES AND MATERIALS | Production and delivery of Grade 1 Mathematics Lesson Exemplars (LEs) and Worksheets (WSs) for School Year 2024-2025 | CID/SDO Angeles City | Competetive Bidding | 2024-09-24 | 2024-09-03 | 2024-09-25 | 2024-10-02 | 2024-09-24 | 2024-10-16 | 2024-09-24 | 2024-10-17 | 2024-10-31 | 2024-11-12 | Sub-Aro | 1324776.96 | 0 | 1390250.63 | 1388470 | 95% Complete | 1388470
SUPPLIES AND MATERIALS | Production and delivery of Kindergarten Lesson Exemplars (LEs) and Worksheets (WSs) for School Year 2024-2025 | CID/SDO Angeles City | [12 empty] | 65473.67 | 0
SUPPLIES AND MATERIALS | Production of Transition Learning Resources of Grade 4 Lesson Exemplars (LEs) and Worksheets (WSs) for the implementation of MATATAG Curriculum for the School Year 2024-2025 | CID/SDO Angeles City | Competetive Bidding | 2024-09-24 | 2024-09-25 | 2024-10-02 | 2024-09-24 | 2024-10-16 | 2024-09-24 | 2024-10-17 | 2024-10-31 | 2024-11-04 | 2024-11-12 | Sub-Aro | 706860 | 0 | 1546637.01 | 1543362 | 85% Complete | 1543362
SUPPLIES AND MATERIALS | Production of Transition Learning Resources of Grade 7 Lesson Exemplars (LEs) and Worksheets (WSs) for the implementation of MATATAG Curriculum for the School Year 2024-2025 | CID/SDO Angeles City | [12 empty] | 839777.01 | 0
SUPPLIES AND MATERIALS | Procurement of Materials for the Printing/Production of Grade 1 Transition Learning Resources Lesson Exemplars (LEs) and Worksheets (WSs) for the implementation of the MATATAG Curriculum for SY 2024-2025 | CID/SDO Angeles City | Competetive Bidding | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-10 | 2024-10-31 | 2024-11-04 | 2024-11-12 | Sub-Aro | 3187125.34 | 0 | 3187125.34 | 3157738 | Completed | 3157738
SUPPLIES AND MATERIALS | Procurement of remediation packages for reading programs | CID/SDO Angeles City | Competetive Bidding | 2024-09-18 | 2024-10-01 | 2024-10-08 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-23 | 2024-11-04 | 5/11/202 | 11/11/202 | Sub-Aro | 2749433.23 | 0 | 2749433.23 | 2749125 | Completed | 2749125
SUPPLIES AND MATERIALS | Procurement of printing and delivery of storybooks for reading programs. | CID/SDO Angeles City | Competetive Bidding | 2024-11-19 | 2024-11-20 | 2024-11-27 | 2024-12-09 | 2024-12-09 | 2024-12-09 | 2024-12-10 | 2024-12-12 | 2024-12-17 | 2024-12-18 | Sub-Aro | 1953684.46 | 0 | 1953684.46 | 1940873.85 | On-going | 1940873.85
SUPPLIES AND MATERIALS | Procurement of Assistive Devices, Equipment, Supplies and Materials for Inclusive Learning Resources Center (ILRC) | CID/SDO Angeles City | Competetive Bidding | 2024-11-07 | 2024-11-08 | 2024-11-15 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-28 | 2024-12-12 | 2024-12-13 | 2024-12-17 | Sub-Aro | 7989075 | 0 | 7989075 | 7838089.82 | On-going | 7838089.82
SUPPLIES AND MATERIALS | Procurement of Learning Tools and Equipment – Technical Vocational Livelihood (LTE-TVL) To Public High School | CID/SDO Angeles City | Competetive Bidding | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-10 | 2024-10-29 | 2024-10-31 | 2024-11-12 | Sub-Aro | 2875845 | 0 | 2875845 | 2099692.666 | Completed | 2099692.666
SUPPLIES AND MATERIALS | Procurement of Goods for the Implementation of School-Based Feeding Program (SBFP) - Milk Feeding Component for SY 2024-2025 | SGOD/SDO Angeles City | Competetive Bidding | 2024-10-16 | 2024-11-12 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-20 | 2024-12-12 | 2024-12-16 | 2024-12-17 | Sub-Aro | 11941482 | 0 | 11941482 | 11941482 | On-going | 11941482
[14 empty] | Total: |  | 0 | 89954045.82 | 81371251.876
DEFINITION | [15 empty] | Remarks
1. PROGRAM (BESF)– A homogeneous group of activities necessary for the performance of a major purpose for which a government agency is established, for the basic maintenance of the agency’s administrative operations or for the provisions of staff support to the agency’s administrative operations or for the provisions of staff support to the agency’s line functions. | [14 empty] | Programs and projects should be alligned with budget documents, and especially those posted at the PhilGeps.
2. PROJECT (BESF)– Special agency undertakings which are to be carried out within a definite time frame and which are intended to result in some pre-determined measure of goods and services.
3. PMO/End User - Unit as proponent of program or project
4. Mode of Procurement - Competitive Bidding and Alternative Methods including: selective bidding, direct contracting, repeat order, shopping, and negotiated procurement.
5. Schedule for Each Procurement Activity - Major procurement activities (pre-procurement conference; advertising/posting; pre-bid conference; eligibility screening; submission and receipt of bids; bid evalutaion; post qualification; award of contract; contract preparation), delivery/completion and acceptance/turnover.
6. Source of Funds - Whether GoP, Foreign Assisted or Special Purpose Fund | [14 empty] | Breakdown into MOOE and
7. Estimated Budget - Agency approved estimate of project/program costs | [14 empty] | any remark that will help
8. Remarks - brief description of program or project | [14 empty] | GPPB track programs and
projects.
| Prepared by: |  |  |  | Recommending approval: | [9 empty] | Approved:
| MARIA CRISTINA S. SARMIENTO |  |  |  | ENRIQUE E. ANGELES JR. PHD, CESO VI | [9 empty] | ENGR. EDGARD C. DOMINGO PHD, CESO V
| BAC Secretariat |  |  |  | Asst. Schools Division Superintendent | [9 empty] | Schools Division Superintendent
Address: Jesus St., Brgy. Pulungbulu, Angeles City, 2009
Telephone No.: (045) 901-9498
Email Address: angeles.city@deped.gov.ph

## 2024 PMR FINAL
Department of Education
Region III
SCHOOLS DIVISION OFFICE OF ANGELES CITY
FY 2024 DepEd Angeles City Procurement Monitoring Report
Code (PAP) | Procurement Program/ Project | PMO/ End-User | Mode of Procurement |  | Schedule for Each Procurement Activity | [8 empty] | Source of Funds | Estimated Budget (PhP) |  |  |  | Remarks (Explaining changes from the APP)
|  |  |  | Pre-Procurement Conference | Ads/ Post of IB/REI | Pre-Bid | Eligibility Check | Sub/ Open of Bids | Bid Evaluation | Post Qualification | Notice of Award | Contract Signing | Notice to Proceed |  | Total | MOOE | CO | CONTRACT AMOUNT
SUPPLIES AND MATERIALS | Procurement of Mathematical Learning Resources (Manipulative Materials) | CID/SDO Angeles City | Competitive Bidding | 2024-02-16 | 20/2/2024 | 2024-02-23 | 2024-06-03 | 2024-06-03 | 2024-06-03 | 2024-07-03 | 2024-11-03 | 21/3/2024 | 2024-03-25 | Sub-Aro | 1032437 | 0 | 1032437 | 488289 | Completed | 488289
SBFP | Procurement of SDO Angeles City Milk Feeding 2023-2024 | SGOD/SDO Angeles City | NP-53.12 Community Participation | 2024-03-01 | 2024-03-08 | 2024-03-10 | 22/3/2024 | 22/3/2024 | 22/3/2024 | 2024-03-23 | 2024-04-01 | 2024-04-02 | 2024-04-08 | Sub-Aro | 6562724.07 | 0 | 6562724.07 | 6465738 | Completed | 6465738
TRAININGS/SEMINARS | Procurement of Venue and Board and Lodging for the Conduct of Division Training of Trainers (DTOT) on Matatag Curriculum | SGOD/SDO Angeles City | Competitive Bidding | 2024-04-11 | 2024-04-22 | 2024-05-15 | 2024-06-05 | 2024-05-28 | 2024-06-05 | 2024-05-29 | 2024-06-13 | 2024-06-14 | 2024-06-22 | Sub-Aro | 2380000 | 0 | 2380000 | 2379990 | Completed
SUPPLIES AND MATERIALS | Procurement of Printing Materials In-house printing of identified lacking Self- Learning Modules (SLMs) for Public School LearnersProcurement of Printing Materials (Inks, A3 Papers, C2S Book Cover Papers, Saddle Sticher) | CID/SDO Angeles City | Competitive Bidding | 2024-05-08 | 2024-05-10 | 2024-05-17 | 29/5/2024 | 2024-05-29 | 29/5/2024 | 2024-05-30 | 2024-03-06 | 14/6/2024 | 2024-06-17 | Sub-Aro | 2099220.8 | 0 | 2099220.8 | 2093606 | From Savings/Completed | 2093606
SBFP | School Based Feeding Program SY 2024-2025 | SGOD/SDO Angeles City | Competitive Bidding | 2024-05-10 | 2024-05-17 | 2024-05-24 | 13/06/2024 | 13/06/2024 | 13/06/2024 | 2024-06-26 | 2024-06-28 | 2024-07-01 | 2024-07-09 | Sub-Aro | 34091750 | 0 | 34091750 | 30760056.25 | On-going | 30760056.25
REPAIR OF SCHOOL BUILDINGS | Procurement of Project under the CY 2024 BEFF, Repair/Rehabilitation of Classrooms Batch 1 at Northville 15 Integrated School, Brgy. Cutud, Angeles City | SGOD/SDO Angeles City | Competetive Bidding | 2024-05-27 | 2024-06-10 | 2024-06-24 | 2024-07-08 | 2024-07-08 | 2024-07-08 | 2024-07-09 | Short of Award | 2024-09-18 | 2024-11-04 | Sub-Aro | 4167750.28 | 0 | 4167750.28 | 4156888.88 | Completed | 4156888.88
TRAININGS/SEMINARS | Procurement Meals for the Conduct of School Based Training of Teachers ((K, 1, 4 and 7) on the Matatag Curriculum) | SGOD/SDO Angeles City | Competetive Bidding | 2024-06-05 | 2024-06-06 | 2024-06-13 | 2024-06-25 | 2024-06-25 | 2024-06-25 | 2024-06-26 | 2024-07-02 | 2024-07-03 | 2024-07-08 | Sub-Aro | 3062500 | 0 | 3062500 | 3060000 | Completed
SUPPLIES AND MATERIALS | Reproduction of NLC Teaching and Learning Resources (Private Printer) | CID/SDO Angeles City | Competetive Bidding | 2024-07-23 | 2024-07-25 | 2024-08-02 | 2024-08-14 | 2024-08-14 | 2024-08-14 | 2024-08-15 | 2024-09-03 | 2024-09-09 | 2024-09-23 | Sub-Aro | 2380000 | 0 | 2380000 | 2367850.41 | 95% Complete | 2367850.41
SUPPLIES AND MATERIALS | Production and delivery of Grade 1 Mathematics Lesson Exemplars (LEs) and Worksheets (WSs) for School Year 2024-2025 | CID/SDO Angeles City | Competetive Bidding | 2024-09-24 | 2024-09-03 | 2024-09-25 | 2024-10-02 | 2024-09-24 | 2024-10-16 | 2024-09-24 | 2024-10-17 | 2024-10-31 | 2024-11-12 | Sub-Aro | 1324776.96 | 0 | 1390250.63 | 1388470 | 95% Complete | 1388470
SUPPLIES AND MATERIALS | Production and delivery of Kindergarten Lesson Exemplars (LEs) and Worksheets (WSs) for School Year 2024-2025 | CID/SDO Angeles City | [12 empty] | 65473.67 | 0
SUPPLIES AND MATERIALS | Production of Transition Learning Resources of Grade 4 Lesson Exemplars (LEs) and Worksheets (WSs) for the implementation of MATATAG Curriculum for the School Year 2024-2025 | CID/SDO Angeles City | Competetive Bidding | 2024-09-24 | 2024-09-25 | 2024-10-02 | 2024-09-24 | 2024-10-16 | 2024-09-24 | 2024-10-17 | 2024-10-31 | 2024-11-04 | 2024-11-12 | Sub-Aro | 706860 | 0 | 1546637.01 | 1543362 | 85% Complete | 1543362
SUPPLIES AND MATERIALS | Production of Transition Learning Resources of Grade 7 Lesson Exemplars (LEs) and Worksheets (WSs) for the implementation of MATATAG Curriculum for the School Year 2024-2025 | CID/SDO Angeles City | [12 empty] | 839777.01 | 0
SUPPLIES AND MATERIALS | Procurement of Materials for the Printing/Production of Grade 1 Transition Learning Resources Lesson Exemplars (LEs) and Worksheets (WSs) for the implementation of the MATATAG Curriculum for SY 2024-2025 | CID/SDO Angeles City | Competetive Bidding | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-10 | 2024-10-31 | 2024-11-04 | 2024-11-12 | Sub-Aro | 3187125.34 | 0 | 3187125.34 | 3157738 | Completed | 3157738
SUPPLIES AND MATERIALS | Procurement of remediation packages for reading programs | CID/SDO Angeles City | Competetive Bidding | 2024-09-18 | 2024-10-01 | 2024-10-08 | 2024-10-22 | 2024-10-22 | 2024-10-22 | 2024-10-23 | 2024-11-04 | 5/11/202 | 11/11/202 | Sub-Aro | 2749433.23 | 0 | 2749433.23 | 2749125 | Completed | 2749125
SUPPLIES AND MATERIALS | Procurement of printing and delivery of storybooks for reading programs. | CID/SDO Angeles City | Competetive Bidding | 2024-11-19 | 2024-11-20 | 2024-11-27 | 2024-12-09 | 2024-12-09 | 2024-12-09 | 2024-12-10 | 2024-12-12 | 2024-12-17 | 2024-12-18 | Sub-Aro | 1953684.46 | 0 | 1953684.46 | 1940873.85 | On-going | 1940873.85
SUPPLIES AND MATERIALS | Procurement of Assistive Devices, Equipment, Supplies and Materials for Inclusive Learning Resources Center (ILRC) | CID/SDO Angeles City | Competetive Bidding | 2024-11-07 | 2024-11-08 | 2024-11-15 | 2024-11-27 | 2024-11-27 | 2024-11-27 | 2024-11-28 | 2024-12-12 | 2024-12-13 | 2024-12-17 | Sub-Aro | 7989075 | 0 | 7989075 | 7838089.82 | On-going | 7838089.82
SUPPLIES AND MATERIALS | Procurement of Learning Tools and Equipment – Technical Vocational Livelihood (LTE-TVL) To Public High School | CID/SDO Angeles City | Competetive Bidding | 2024-09-18 | 2024-09-20 | 2024-09-27 | 2024-10-09 | 2024-10-09 | 2024-10-09 | 2024-10-10 | 2024-10-29 | 2024-10-31 | 2024-11-12 | Sub-Aro | 2875845 | 0 | 2875845 | 2099692.666 | Completed | 2099692.666
SUPPLIES AND MATERIALS | Procurement of Goods for the Implementation of School-Based Feeding Program (SBFP) - Milk Feeding Component for SY 2024-2025 | SGOD/SDO Angeles City | Competetive Bidding | 2024-10-16 | 2024-11-12 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-19 | 2024-11-20 | 2024-12-12 | 2024-12-16 | 2024-12-17 | Sub-Aro | 11941482 | 0 | 11941482 | 11941482 | On-going | 11941482
[14 empty] | Total: |  | 0 | 89409914.82 | 84431251.876
| Prepared by: |  |  |  | Recommending approval: | [7 empty] | Approved: |  | Approved:
| MARIA CRISTINA S. SARMIENTO |  |  |  | ENRIQUE E. ANGELES JR. PHD, CESO VI | [7 empty] | ENGR. EDGARD C. DOMINGO PHD, CESO V
| BAC Secretariat |  |  |  | Asst. Schools Division Superintendent | [7 empty] | Schools Division Superintendent
Address: Jesus St., Brgy. Pulungbulu, Angeles City, 2009
Telephone No.: (045) 901-9498
Email Address: angeles.city@deped.gov.ph

## PMR 2022 (hidden)
CY 2022 SDO ANGELES CITY PROCUREMENT MONITORING REPORT
Code (UACS/PAP) | Procurement Program/Project | PMO/ End-User | PMO/ End-User | Mode of Procurement | Actual Procurement Activity | [11 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  | List of Invited Observers | Date of Receipt of Invitation | [5 empty] | Remarks (Explaining changes from the APP)
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total | MOOE | CO |  | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Delivery/ Completion/ Acceptance (If applicable)
COMPLETED PROCUREMENT ACTIVITIES
1 | CY2022 BEFF Repair of Classroom School Building at Lourdes North West Elementary School | SDO Angeles City | LNWES | Competitive Bidding | June 20, 2022 | June 24-July 13, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | Sept. 9, 2022 | Sept. 12, 2022 | Sept. 20, 2022 |  |  | BEFF CY 2022 REPAIR OF CLASSROOM |  |  | 2750000 | 2739845.02 |  |  | COA and ACPST-CCI | June 24, 2022 | July 6, 2022 | July 6, 2022 | July 6, 2022 | July 14, 2022 |  | Completed
2 | CY2022 BEFF Repair of Classroom School Building at Virgen Delos Remedios Elementary School | SDO Angeles City | VDRES | Competitive Bidding | June 20, 2022 | June 24-July 13, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | Sept. 9, 2022 | Sept. 12, 2022 | Sept. 20, 2022 |  |  | BEFF CY 2022 REPAIR OF CLASSROOM |  |  | 2100000 | 2088366.63 |  |  | COA and ACPST-CCI | June 24, 2022 | July 6, 2022 | July 6, 2022 | July 6, 2022 | July 14, 2022 |  | Completed
3 | CY2022 BEFF Repair of Classroom School Building at Dr. Clemente N. Dayrit Sr. Elementary School | SDO Angeles City | CLEMENDES | Competitive Bidding | June 20, 2022 | June 24-July 13, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | Sept. 9, 2022 | Sept. 12, 2022 | Sept. 20, 2022 |  |  | BEFF CY 2022 REPAIR OF CLASSROOM |  |  | 1500000 | 1490072.29 |  |  | COA and ACPST-CCI | June 24, 2022 | July 6, 2022 | July 6, 2022 | July 6, 2022 | July 14, 2022 |  | Completed
4 | CY2022 BEFF Repair of Classroom School Building at DON AMBROCIO MENDIOLA INTEGRATED School | SDO Angeles City | DAMIS | Competitive Bidding | June 20, 2022 | June 24-July 13, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | Sept. 9, 2022 | Sept. 12, 2022 | Sept. 20, 2022 |  |  | BEFF CY 2022 REPAIR OF CLASSROOM |  |  | 1650000 | 1640121 |  |  | COA and ACPST-CCI | June 24, 2022 | July 6, 2022 | July 6, 2022 | July 6, 2022 | July 14, 2022 |  | Completed
[20 empty] | 8000000 | 7958404.94 |  |  | 41595.06
GOODS
1 | Printing Services for the Development and Production of Self Learning Modules for Quarter 3 SY 2021-2022 Lot 1 | SDO Angeles City | All public Schools | Competitive Bidding | Dec 9, 2021 | Dec 14, 2021 | Dec 22, 2021 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 5, 2022 | Feb 9, 2022 | Feb. 14, 2022 | Feb. 15, 2022 | 45 days | March 31, 2022 | GAA |  |  | 9902000 | 8888035.2 |  |  | COA and ACPST-CCI | Dec 14, 2021 | Dec 28, 2021 | Dec 28, 2021 | Dec 28, 2021 | Dec 28, 2021 |  | Completed
2 | Printing Services for the Development and Production of Self Learning Modules for Quarter 4 SY 2021-2022 Lot 2 | SDO Angeles City | All public Schools | Competitive Bidding | Dec 9, 2021 | Dec 14, 2021 | Dec 22, 2021 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 4, 2022 | Jan. 5, 2022 | Feb 9, 2022 | Feb. 14, 2022 | Feb. 15, 2022 | 45 days | March 31, 2022 | GAA |  |  | 6313000 | 5679174.8 |  |  | COA and ACPST-CCI | Dec 14, 2021 | Dec 28, 2021 | Dec 28, 2021 | Dec 28, 2021 | Dec 28, 2021 |  | Completed
3 | Procurement of USB -OTG from Savings of the Development and Production of Self Learning Modules | SDO Angeles City | All public Schools | Competitive Bidding | Jan 27, 2022 | Feb 8-22, 2022 | Feb. 15, 2022 | Feb 22, 2022 | Feb 22, 2022 | Feb 22, 2022 | Feb 23, 2022 | Apr 29, 2022 | May 2, 2022 | May 11, 2022 | 30 days | June 9, 2022 | GAA |  |  | 1647790 | 1345249.6 |  |  | COA and ACPST-CCI | Feb 8, 2022 | Feb 15, 2022 | Feb 15, 2022 | Feb 15, 2022 | Feb 15, 2022 |  | Completed
5 | School-Based Feeding Program | SDO Angeles City | All public Schools | Competitive Bidding | Mar 25, 2022 | Apr 4-19, 2022 | Apr 12, 2022 | Apr 25, 2022 | Apr 25, 2022 | Apr 25, 2022 | Apr 28, 2022 | Apr 29, 2022 | May 2, 2022 | May 13. 2022 | 30 days | June 11, 2022 | GAA |  |  | 6437880 | 5674872 |  |  | COA and ACPST-CCI | Apr 4, 2022 | Apr 18, 2022 | Apr 18, 2022 | Apr 18, 2022 | Apr 18, 2022 |  | Completed
7 | Procurement of Bluetooth Speakers from CY2022 Savings | SDO Angeles City | All public Schools | Competitive Bidding | May 19, 2022 | June 23-30, 2022 | July 1, 2022 | July 13, 2022 | July 13, 2022 | July 13, 2022 | July 21, 2022 | July 25, 2022 | July 27, 2022 | Aug 8, 2022 | 45 days | September 21, 2022 | GAA |  |  | 14245829.2 | 9768384 |  |  | COA and ACPST-CCI | June 23, 2022 | July 7, 2022 | July 7, 2022 | July 7, 2022 | July 7, 2022 |  | Completed
8 | Procurement of DEpEd Computerization Program | SDO Angeles City | All public Schools | Competitive Bidding | July 25, 2022 | August 1-17, 2022 | August 5, 2022 | August 18, 2022 | August 18, 2022 | August 18, 2022 | August 22, 2022 | August 30, 2022 | August 31, 2022 | September 21, 2022 | 30 days | October 13, 2022 | GAA |  |  | 1000000 | 998000 |  |  | COA and ACPST-CCI | [6 empty] | Completed
9 | Procurement of Printer's Inks from 2022 Savings | SDO Angeles City | All public Schools | Competitive Bidding | August 15, 2022 | August 17-23, 2022 | August 23, 2022 | September 5, 2022 | September 5, 2022 | September 5, 2022 | September 6, 2022 | September 13, 2022 | September 14, 2022 | September 21, 2022 | 30 days | October 4, 2022 | GAA |  |  | 2346600 | 1583010 |  |  | COA and ACPST-CCI | [6 empty] | Completed
10 | Procurement of Bondpapers from 2022 Savings | SDO Angeles City | All public Schools | Competitive Bidding | September 14, 2022 | September 14-21,2022 | September 21, 2022 | October 5, 2022 | October 5, 2022 | October 5, 2022 | October 6, 2022 | October 11, 2022 | October 12, 2022 | October 18, 2022 | 30 days | November 24, 2022 | GAA |  |  | 2100845.2 | 2100830 |  |  | COA and ACPST-CCI | [6 empty] | Completed
11 | CY2022 CONVERSION OF SPED CENTER TO INCLUSIVE LEARNING RESOURCE CENTER (ILRC) | SDO Angeles City | Angeles ES | Competitive Bidding | October 21, 2022 | October 25, 2022 | November 2, 2022 | November 14, 2022 | November 14, 2022 | November 14, 2022 | November 15, 2022 | November 22, 2022 | November 23, 2022 | December 5, 2022 | 90 days |  | GAA |  |  | 3600000 | 3589571.21 |  |  | COA and ACPST-CCI | [6 empty] | On Going
[20 empty] | 47593944.4 | 39627126.81
[20 empty] | 7966817.59 | 0
Prepared by: |  |  |  | Recommended for Approval by: | [7 empty] | Approved: | [10 empty] | APPROVED: |  |  | Approved:
MARIA CRISTINA S. SARMIENTO |  |  |  | FERNANDINA P. OTCHENGCO, PhD CESE | [7 empty] | MA. IRELYN P. TAMAYO PhD, CESO V | [10 empty] | MA. IRELYN P. TAMAYO, PhD CESE |  |  | MA. IRELYN P. TAMAYO PhD, CESO V
BAC Secretariat |  |  |  | BAC Chairperson | [7 empty] | Head of Procuring Entity | [10 empty] | Head of the Procuring Entity |  |  | Head of Procuring Entity