## PMR
DepEd Schools Division of Angeles City | [9 empty] | Procurement Monitoring Report as of June 30, 2026
[5 empty] | Actual Procurement Activities | [13 empty] | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  | Date of Receipt of Invitation
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
COMPLETED PROCUREMENT ACTIVITIES
TRAININGS/SEMINARS | Division Seminar-Workshop on the Reconciliation and Consolidation of CY 2025 Year End Financial Reports | Budget Officer | No | Small Value Procurement | N/A | N/A | N/A | 2026-01-06 | N/A | 2026-01-06 | N/A | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-06 | 2026-01-08 | 2026-01-08 | Division MOOE | 40000 | 40000 | 40000 | 40000 | 40000 | 40000 | N/A | N/A | 2026-01-06 | N/A | 2026-01-06 | N/A | 2026-01-08 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conduct of FY 2026 SGOD PIR and Performance Evaluation (January 14, 2026) | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2025-01-09 | N/A | 2025-01-09 | N/A | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-14 | 2025-01-14 | Division MOOE | 12000 | 12000 | 12000 | 11850 | 11850 | 11850 | N/A | N/A | 2025-01-09 | N/A | 2025-01-09 | N/A | 2026-01-14 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conductof FY 2026 DIVISION PIR and Performance Evaluation (January 15-16, 2026) | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2025-01-09 | N/A | 2025-01-09 | N/A | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-09 | 2025-01-15 | 2025-01-16 | Division MOOE | 40000 | 40000 | 40000 | 39500 | 39500 | 39500 | N/A | N/A | 2025-01-09 | N/A | 2025-01-09 | N/A | 2026-01-16 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conductof FY 2026 SGOD PIR and Performance Evaluation (April 13, 2026) Moved April 16, 2026 | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-01-21 | 2026-01-21 | 2026-02-18 | 2026-02-18 | 2026-04-16 | 2026-04-16 | Division MOOE | 12000 | 12000 | 12000 | 11850 | 11850 | 11850 | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-04-16 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conductof FY 2026 DIVISION PIR and Performance Evaluation (April 17,2026) Moved on April 21, 2026 | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-01-21 | 2026-01-21 | 2026-02-18 | 2026-02-18 | 2026-04-21 | 2026-04-21 | Division MOOE | 20000 | 20000 | 20000 | 19750 | 19750 | 19750 | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-04-21 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conductof FY 2026 SGOD PIR and Performance Evaluation (July 8, 2026) reshed on June 29, 2026 | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-01-21 | 2026-01-21 | 2026-02-18 | 2026-02-18 | 2026-06-29 | 2026-06-29 | Division MOOE | 12000 | 12000 | 12000 | 11850 | 11850 | 11850 | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-06-29 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conductof FY 2026 DIVISION PIR and Performance Evaluation (July 13-14, 2026) reshed on June 30, 2026 to July 1, 2026 | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-01-21 | 2026-01-21 | 2026-02-18 | 2026-02-18 | 2026-07-01 | 2026-07-01 | Division MOOE | 40000 | 40000 | 40000 | 39500 | 39500 | 39500 | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-07-01 | Completed
REPAIR AND MAINTENANCE | Maintenance & Servicing of Service Vehicle (Avanza-A7K625) | SUPPLY OFFICER | No | Direct Acquisition | N/A | N/A | N/A | 2026-01-16 | N/A | 2026-01-16 | N/A | 2026-01-16 | 2026-01-16 | 2026-01-21 | 2026-01-21 | 2026-01-23 | 2026-01-23 | Division MOOE | 18000 | 18000 | 18000 | 16842.09 | 16842.09 | 16842.09 | N/A | N/A | 2026-01-16 | N/A | 2026-01-16 | N/A | 2026-01-23 | Completed
SUPPLIES AND MATERIALS | Procurement of Stamp of Ownership Device | LIBRARIAN II | No | Small Value Procurement | N/A | N/A | N/A | 29-01-2026 | N/A | 29-01-2026 | N/A | 29-01-2026 | 29-01-2026 | 2026-02-20 | 2026-02-20 | 2026-03-19 | 2026-03-19 | Division MOOE | 2490 | 2490 | 2490 | 2490 | 2490 | 2490 | N/A | N/A | 29-01-2026 | N/A | 29-01-2026 | N/A | 2026-03-19 | Completed
SUPPLIES AND MATERIALS | Purchase of Toners for Division Office Copiers | SUPPLY OFFICER | No | Direct Acquisition | N/A | N/A | N/A | 2026-01-27 | N/A | 2026-01-27 | N/A | 2026-01-27 | 2026-01-27 | 2026-02-16 | 2026-02-16 | 2026-02-18 | 2026-02-18 | Division MOOE | 20000 | 20000 | 20000 | 20000 | 20000 | 20000 | N/A | N/A | 2026-01-27 | N/A | 2026-01-27 | N/A | 2026-02-18 | Completed
SUPPLIES AND MATERIALS | Procurement of 1st Quarter Common use supplies 2026 | SUPPLY OFFICER | No | Small Value Procurement | N/A | N/A | N/A | 2026-01-28 | N/A | 2026-01-28 | N/A | 2026-01-28 | 2026-01-28 | 2026-02-11 | 2026-02-11 | 2026-03-11 | 2026-03-11 | Division MOOE | 175852.79 | 175852.79 | 175852.79 | 128631.93 | 128631.93 | 128631.93 | N/A | N/A | 2026-01-28 | N/A | 2026-01-28 | N/A | 2026-03-11 | Completed
TRAININGS/SEMINARS | Procurement of Meals during the Division Accreditation and Refresher Course on Sports Coaching and Officiating of Combative and Non Combative Sports in Preparation for CLRAA Meet 2026 and Palaro Pambansa 2026 | EPS-SGOD/DSO | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-03 | N/A | 2026-02-03 | N/A | 2026-02-03 | 2026-02-03 | 2026-02-06 | 2026-02-06 | 2026-02-28 | 2026-02-28 | Division MOOE | 150000 | 150000 | 150000 | 150000 | 150000 | 150000 | N/A | N/A | 2026-02-03 | N/A | 2026-02-03 | N/A | 2/282026 | Completed
TRAININGS/SEMINARS | Division Seminar-Workshop on Preparing Comprehensive Action Research June 19, 2026 | EPS-SGOD/DSO | No | Small Value Procurement | N/A | N/A | N/A |  | N/A |  | N/A | [6 empty] | Division MOOE | 40000 | 40000 | 40000 | 0 |  |  | N/A | N/A |  | N/A |  | N/A |  | Cancelled
SUPPLIES AND MATERIALS | Purchase of Dental Supplies in Providing Dental Services | DENTIST II | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-19 | N/A | 2026-02-19 | N/A | 2026-02-19 | 2026-02-19 | 2026-03-11 | 2026-03-11 | 2026-04-06 | 2026-04-06 | Division MOOE | 40000 | 40000 | 40000 | 38375.6 | 38375.6 | 38375.6 | N/A | N/A | 2026-02-19 | N/A | 2026-02-19 | N/A | 2026-04-06 | Completed
SUPPLIES AND MATERIALS | Purchase of Medical Supplies for providing Medical Services | NURSE II - NIC | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-02-16 | 2026-02-16 | 2026-03-11 | 2026-03-11 | 2026-03-30 | 2026-03-30 | Division MOOE | 80000 | 80000 | 80000 | 80000 | 80000 | 80000 | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-03-30 | Terminated due to default delivery
TRAININGS/SEMINARS | Procurement of Meals for the Capacity Building on Research on: Writing High Quality Research Proposals Aligned with the DepEd Research Agenda May 13-14, 2026 | SEPS-PAR | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-06 | N/A | 2026-02-06 | N/A | 2026-02-06 | 2026-02-06 | 2026-04-07 | 2026-04-07 | 2026-05-13 | 2026-05-14 | Division MOOE | 59000 | 59000 | 59000 | 46020 | 46020 | 46020 | N/A | N/A | 2026-02-06 | N/A | 2026-02-06 | N/A | 2026-05-14 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Division Validation on the SGC Functionality of Elementary Schools | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-02-16 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 2026-02-24 | 2026-02-24 | Division MOOE | 44875 | 44875 | 44875 | 44875 | 44875 | 44875 | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-03-24 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Evaluation and Validation of SGC Functionality of the Elementary Schools by the Regional Office | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-02-16 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 2026-03-13 | 2026-03-13 | Division MOOE | 35250 | 33250 | 33250 | 35250 | 35250 | 35250 | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-03-13 | Completed
REPAIR AND MAINTENANCE | Avanza Stabilizer adn Brake Pads/Shoe Replacement and Servicing (SNE 6558) | SUPPLY OFFICER | No | Direct Acquisition | N/A | N/A | N/A | 2026-02-09 | N/A | 2026-02-09 | N/A | 2026-02-09 | 2026-02-09 | 2026-02-12 | 2026-02-12 | 2026-02-16 | 2026-02-16 | Division MOOE | 28799.63 | 28799.63 | 28799.63 | 28799.63 | 28799.63 | 28799.63 | N/A | N/A | 2026-02-09 | N/A | 2026-02-09 | N/A | 2026-02-16 | Completed
SUPPLIES AND MATERIALS | Purchase of Division Office Flag | SUPPLY OFFICER | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-19 | N/A | 2026-02-19 | N/A | 2026-02-19 | 2026-02-19 | 2026-03-05 | 2026-03-05 | 2026-03-10 | 2026-03-10 | Division MOOE | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | N/A | N/A | 2026-02-19 | N/A | 2026-02-19 | N/A | 2026-03-10 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conduct of Demonstration- Teaching Reflection for the Teacher-Applicants | ADMIN OFFICER V | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-06 | N/A | 2026-02-06 | N/A | 2026-02-06 | 2026-02-06 | 2026-02-09 | 2026-02-09 | 2026-02-10 | 2026-02-11 | Division MOOE | 61200 | 61200 | 61200 | 61200 | 61200 | 61200 | N/A | N/A | 2026-02-06 | N/A | 2026-02-06 | N/A | 2026-02-11 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Revisiting of the Guidelines on the Pilot Implementation of the Strengthened Senior High School Curriculum for Grade 11 (SY 2025–2026) and the Pilot Implementation of the Enhanced Work Immersion Program | EDUCATION PROGRAM SUPERVISOR | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-06 | N/A | 2026-02-06 | N/A | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-06 | 2026-02-09 | 2026-02-09 | School MOOE | 17500 | 17500 | 17500 | 17500 | 17500 | 17500 | N/A | N/A | 2026-02-06 | N/A | 2026-02-06 | N/A | 2026-02-09 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Intensive Training for 2026 Regional School Press Conference Qualifiers | EDUCATION PROGRAM SUPERVISOR | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-02-16 | 2026-02-16 | 2026-02-20 | 2026-02-20 | 2026-02-28 | 2026-02-28 | School MOOE | 62850 | 62850 | 62850 | 62850 | 62850 | 62850 | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-02-28 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Division-Training in Data-Informed Instructional Refinement in the ARAL-Reading | EDUCATION PROGRAM SUPERVISOR | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | Division MOOE | 180000 | 180000 | 180000 | 178000 | 178000 | 178000 | N/A | N/A | N/A | N/A | N/A | N/A |  | Cancelled
SUPPLIES AND MATERIALS | Procurement of Materials for the Division-Training in Data-Informed Instructional Refinement in the ARAL-Reading | EDUCATION PROGRAM SUPERVISOR | No | Small Value Procurement | N/A | N/A | N/A | 2026-03-05 | N/A | 2026-03-05 | N/A | 2026-03-05 | 2026-03-05 | 2026-04-16 | 2026-04-16 | 2026-04-29 | 2026-04-29 | Division MOOE | 6200 | 6200 | 6200 | 0 |  |  | N/A | N/A | 2026-03-05 | N/A | 2026-03-05 | N/A | 2026-04-29 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Division-Training on Enhancing Instructional Refinement in the Implementation of the Revised K to 12 Curriculum in Kindergarten | EDUCATION PROGRAM SUPERVISOR | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | [5 empty] | Division MOOE | 142500 | 142500 | 142500 | 141075 | 141075 | 141075 | N/A | N/A | N/A | N/A | N/A | N/A |  | Cancelled
SUPPLIES AND MATERIALS | Procurement of Materials for the Division-Training on Enhancing Instructional Refinement in the Implementation of the Revised K to 12 Curriculum in Kindergarten | EDUCATION PROGRAM SUPERVISOR | No | Small Value Procurement | N/A | N/A | N/A | 2026-03-05 | N/A | 2026-03-05 | N/A | 2026-03-05 | 2026-03-05 | 2026-04-16 | 2026-04-16 | 2026-04-29 | 2026-04-29 | Division MOOE | 7500 | 7500 | 7500 | 0 |  |  | N/A | N/A | 2026-03-05 | N/A | 2026-03-05 | N/A | 2026-04-29 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Division Seminar on Laws and Regulations on Government Expenditures | SEPS | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-23 | N/A | 2026-02-23 | N/A | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-26 | 2026-02-26 | Division MOOE | 116400 | 116400 | 116400 | 116400 | 116400 | 116400 | N/A | N/A | 2026-02-23 | N/A | 2026-02-23 | N/A | 2026-02-26 | Completed
SUPPLIES AND MATERIALS | Procurement of Mattresses for Student-Athletes during the Pariticipation of SDO Angeles City in the CLRAA Meet 2026 | EPS-SGOD/DSO | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-02-16 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-03-02 | 2023-03-02 | Saro No. OSEC 3-25-0439 | 109500 | 109500 | 109500 | 109500 | 109500 | 109500 | N/A | N/A | 2026-02-16 | N/A | 2026-02-16 | N/A | 2026-03-02 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conduct of Division Welfare Program (Lenten Recollection for Division Office Personnel) | SEPS | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-25 | N/A | 2026-02-25 | N/A | 2026-02-25 | 2026-02-25 | 2026-03-11 | 2026-03-11 | 2026-03-23 | 2026-03-23 | Division MOOE | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | N/A | N/A | 2026-02-25 | N/A | 2026-02-25 | N/A | 2026-03-23 | Completed
TRAININGS/SEMINARS | Procurement of Meals of the Conduct of Division Women's Month Celebration | SEPS | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-25 | N/A | 2026-02-25 | N/A | 2026-02-25 | 2026-02-25 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | Division MOOE | 11000 | 11000 | 11000 | 11000 | 11000 | 11000 | N/A | N/A | 2026-02-25 | N/A | 2026-02-25 | N/A | 2026-03-12 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conduct of Division Management Committee Meeting | SEPS | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-25 | N/A | 2026-02-25 | N/A | 2026-02-25 | 2026-02-25 | 2026-03-02 | 2026-03-02 | 2026-03-03 | 2026-03-03 | Division MOOE & School MOOE | 48000 | 48000 | 48000 | 37050 | 37050 | 37050 | N/A | N/A | 2026-02-25 | N/A | 2026-02-25 | N/A | 2026-03-03 | Completed
TRAININGS/SEMINARS | Procurement of Meals and Accomodation for the Division Training on Leadership with Emotional Inteliigence of SDO Angeles City | SEPS | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-27 | N/A | 2026-02-27 | N/A | 2026-02-27 | 2026-02-27 | 2026-03-16 | 2026-03-16 | 2026-03-17 | 2026-03-19 | Division MOOE | 600000 | 600000 | 600000 | 600000 | 600000 | 600000 | N/A | N/A | 2026-02-27 | N/A | 2026-02-27 | N/A | 2026-03-19 | Completed
SUPPLIES AND MATERIALS | Purchase of Garden Hose and Accessories Admin Office | AOV -ADMIN | No | Small Value Procurement | N/A | N/A | N/A | 2026-04-14 | N/A | 2026-04-14 | N/A | 2026-04-14 | 2026-04-14 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | Division MOOE | 4340 | 4340 | 4340 | 4340 | 4340 | 4340 | N/A | N/A | 2026-04-14 | N/A | 2026-04-14 | N/A | 2026-06-02 | Completed
SUPPLIES AND MATERIALS | Procurement of Water Storage Drums Water for Comfort Rooms | AOV -ADMIN | No | Small Value Procurement | N/A | N/A | N/A | 2026-04-16 | N/A | 2026-04-16 | N/A | 2026-04-16 | 2026-04-16 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | Division MOOE | 6000 | 6000 | 6000 | 5940 | 5940 | 5940 | N/A | N/A | 2026-04-16 | N/A | 2026-04-16 | N/A | 2026-06-02 | Completed
SUPPLIES AND MATERIALS | Purchase of Lighting Bulbs in Gabaldon Building and Libruary Hub | AOV -ADMIN | No | Small Value Procurement | N/A | N/A | N/A | 2026-04-14 | N/A | 2026-04-14 | N/A | 2026-04-14 | 2026-04-14 | 2026-06-02 | 2026-06-02 | 2026-06-02 | 2026-06-02 | Division MOOE | 2800 | 2800 | 2800 | 2800 | 2800 | 2800 | N/A | N/A | 2026-04-14 | N/A | 2026-04-14 | N/A | 2026-06-02 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Coordination Meeting for the Implementation of SDO-Based Payroll Processing | AOV -ADMIN | No | Small Value Procurement | N/A | N/A | N/A | 2026-03-06 | N/A | 2026-03-06 | N/A | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-06 | 2026-03-09 | 2026-03-09 | Division MOOE | 6750 | 6750 | 6750 | 6750 | 6750 | 6750 | N/A | N/A | 2026-03-06 | N/A | 2026-03-06 | N/A | 2026-03-09 | Completed
TRAININGS/SEMINARS | Provision of Transportation Services for the 2026 Regional Festival of Talents March 13-15, 2026 | EPS | No | Small Value Procurement | N/A | N/A | N/A | 2026-03-10 | N/A | 2026-03-10 | N/A | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-15 | Division MOOE | 33000 | 33000 | 33000 | 33000 | 33000 | 33000 | N/A | N/A | 2026-03-10 | N/A | 2026-03-10 | N/A | 2026-03-15 | Completed
TRAININGS/SEMINARS | Provision of Meals for the 2026 Regional Festival of Talents March 13-15, 2026 | EPS | No | Small Value Procurement | N/A | N/A | N/A | 2026-03-10 | N/A | 2026-03-10 | N/A | 2026-03-10 | 2026-03-10 | 2026-03-12 | 2026-03-12 | 2026-03-13 | 2026-03-15 | Division MOOE & School MOOE | 130500 | 130500 | 130500 | 130500 | 130500 | 130500 | N/A | N/A | 2026-03-10 | N/A | 2026-03-10 | N/A | 2026-03-15 | Completed
TRAININGS/SEMINARS | Provision of Meals for the 2026 Regional Schools Press Conference (RSPC) Delegation of the Schools Division of Angeles City | EPS | No | Small Value Procurement | N/A | N/A | N/A | 2026-03-13 | N/A | 2026-03-13 | N/A | 2026-03-13 | 2026-03-13 | 2026-03-17 | 2026-03-17 | 2026-03-20 | 2026-03-20 | Division MOOE & School MOOE | 420750 | 420750 | 420750 | 392700 | 392700 | 392700 | N/A | N/A | 2026-03-13 | N/A | 2026-03-13 | N/A | 2026-03-20 | Completed
REPAIR AND MAINTENANCE | Maintenance & Servicing of Division Service Vehicle Van (SND 8517) | SUPPLY OFFICER | No | Direct Acquisition | N/A | N/A | N/A | 2026-03-09 | N/A | 2026-03-09 | N/A | 2026-03-09 | 2026-03-09 | 2026-03-11 | 2026-03-11 | 2026-03-12 | 2026-03-12 | Division MOOE | 17821.34 | 17821.34 | 17821.34 | 17821.34 | 17821.34 | 17321.34 | N/A | N/A | 2026-03-09 | N/A | 2026-03-09 | N/A | 2026-03-12 | Completed
SUPPLIES AND MATERIALS | Purchase of Toner for HR Office Copiers | SUPPLY OFFICER | No | Direct Acquisition | N/A | N/A | N/A | 2026-03-13 | N/A | 2026-03-13 | N/A | 2026-03-13 | 2026-03-13 | 2026-06-02 | 2026-06-02 | 2026-06-18 | 2026-06-18 | Division MOOE | 18523.98 | 18523.98 | 18523.98 | 18523.98 | 18523.98 | 18523.98 | N/A | N/A | 2026-03-13 | N/A | 2026-03-13 | N/A | 2026-06-18 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Commission on Audit Exit Conference for CY 2025 | BUDGET OFFICER | No | Small Value Procurement | N/A | N/A | N/A | 2026-03-23 | N/A | 2026-03-23 | N/A | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-24 | 2026-03-24 | Division MOOE | 7500 | 7500 | 7500 | 7500 | 7500 | 7500 | N/A | N/A | 2026-03-23 | N/A | 2026-03-23 | N/A | 2026-03-24 | Completed
REPAIR AND MAINTENANCE | Servicing & Maintenance of Division Office Service Pick-Up (B7-M649) | SUPPLY OFFICER | No | Direct Contracting | N/A | N/A | N/A | 2026-03-25 | N/A | 2026-03-25 | N/A | 2026-03-25 | 2026-03-25 | 2026-04-07 | 2026-04-07 | 2026-04-07 | 2026-04-07 | Division MOOE | 20405 | 20405 | 20405 | 20405 | 20405 | 20405 | N/A | N/A | 2026-03-25 | N/A | 2026-03-25 | N/A | 2026-04-07 | Completed
SUPPLIES AND MATERIALS | Procurement of Supplementary Learning Resoruces for School Libraries Lot 6 | EPSvr-LRMDS | No | Direct Contracting | N/A | N/A | N/A | 2026-05-26 | N/A | 2026-05-26 | N/A | 2026-05-26 | 2026-05-26 | 2026-06-06 | 2026-06-06 | 2026-06-09 | 2026-06-09 | DEPED-ROIII-2025-06-1227 SUB-ARO | 12480 | 12480 | 12480 | 12480 | 12480 | 12480 | N/A | N/A | 2026-05-26 | N/A | 2026-05-26 | N/A | 2026-06-09 | Completed
SUPPLIES AND MATERIALS | Procurement of Supplementary Learning Resoruces for School Libraries Lot 19 | EPSvr-LRMDS | No | Direct Contracting | N/A | N/A | N/A | 2026-05-25 | N/A | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-09 | 2026-06-09 | DEPED-ROIII-2025-06-1227 SUB-ARO | 25980 | 25980 | 25980 | 25980 | 25980 | 25980 | N/A | N/A | 2026-05-25 | N/A | 2026-05-25 | N/A | 2026-06-09 | Completed
REPAIR AND MAINTENANCE | Aircon Cleaning Service for SDO Angeles | SUPPLY OFFICER | No | Small Value Procurement | N/A | N/A | N/A | 2026-05-25 | N/A | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-05-05 | 2026-05-05 | 2026-06-25 | 2026-06-25 | DIVISION MOOE | 59000 | 59000 | 59000 | 59000 | 59000 | 59000 | N/A | N/A | 2026-05-25 | N/A | 2026-05-25 | N/A | 2026-06-25 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conduct if Division Training on Revised k to 12 for the Grade 6, 9 and 10 | SEPS | No | Competitive Bidding | 2026-04-23 | 2026-04-28 | 2026-05-05 | 2026-05-20 | 2026-05-20 | 2026-05-20 | 2026-05-21 | 2026-05-21 | 2026-05-21 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-26 | DEPED ROIII 2026-04-0360 | 2316000 | 2316000 | 2316000 | 2316000 | 2316000 | 2316000 | N/A | 2026-05-05 | 2026-05-20 | 2026-05-20 | 2026-05-01 | 2026-05-21 | 2026-05-26 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Orientation on the Learning System s Strand Policies for the Select Schools Division Office Personnel and School Heads | PSDS | No | Direct Acquisition | N/A | N/A | N/A | 2026-04-28 | N/A | 2026-04-28 | N/A | 2026-04-28 | 2026-04-28 | 2026-04-29 | 2026-04-29 | 2026-04-29 | 2026-04-29 | Division MOOE | 33600 | 33600 | 33600 | 33600 | 33600 | 33600 | N/A | 2026-04-28 | N/A | 2026-04-28 | N/A | N/A | 2026-04-29 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conduct of the School-Based Feeding Program (SBFP) Implementation Review for SY 2025-2026 cum Pre-Planning for SBFP Implementation for SY 2026-2027 | NURSE II - NIC | No | Small Value Procurement | N/A | N/A | N/A | 2026-04-29 | N/A | 2026-04-29 | N/A | 2026-04-29 | 2026-04-29 | 2026-05-04 | 2026-05-05 | 2026-05-05 | 2026-05-06 | DEPED-ROIII-2024-03-0230 SBFP PROGRAM SUPPORT FUNDS | 70000 | 70000 | 70000 | 70000 | 70000 | 70000 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conduct of Project Saktong ALS: Summer Program on Micro-Certification for Professional and Resilient ALS Learners | EPS | No | Direct Aquisition | N/A | N/A | N/A | 2026-05-14 | N/A | 2026-05-14 | N/A | 2026-05-14 | 2026-05-14 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | DEPED ROIII 2026-04-0464 | 93000 | 93000 | 93000 | 89125 | 89125 | 89125 | N/A | N/A | 2026-05-14 | N/A | 2026-05-14 | N/A | 2026-05-25 | Completed
TRAININGS/SEMINARS | Procurement of Materials for the Conduct of Project Saktong ALS: Summer Program on Micro-Certification for Professional and Resilient ALS Learners | EPS | No | Direct Aquisition | N/A | N/A | N/A | 2026-05-20 | N/A | 2026-05-20 | N/A | 2026-05-20 | 2026-05-20 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | DEPED ROIII 2026-04-0464 | 10100 | 10100 | 10100 | 8440 | 8440 | 8440 | N/A | N/A | 2026-05-20 | N/A | 2026-05-20 | N/A | 2026-05-25 | Completed
TRAININGS/SEMINARS | Procurement of Meals and Accomodation for the UNICEF Facilitators for the Conduct of Project Saktong ALS: Summer Program on Micro-Certification for Professional and Resilient ALS Learners | EPS | No | Direct Aquisition | N/A | N/A | N/A | 2026-05-21 | N/A | 2026-05-21 | N/A | 2026-05-21 | 2026-05-21 | N/A | N/A | N/A | N/A | DEPED ROIII 2026-04-0464 | 6000 | 6000 | 6000 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | Cancelled
SUPPLIES AND MATERIALS | Purchase of 2nd Quarter Supplies 2026 | AO IV-SUPPLY OFFICER | No | Small Value Procurement | N/A | N/A | N/A | 2026-05-25 | N/A | 2026-05-25 | N/A | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-17 | 2026-06-17 | Division MOOE | 98268.39 | 98268.39 | 98268.39 | 71760.14 | 71760.14 | 71760.14 | N/A | N/A | 2026-06-01 | N/A | 2026-06-01 | N/A | 2026-06-17 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the 2026 Brigada Eskwela Kick-Off | EPS II/SEPS | No | Small Value Procurement | N/A | N/A | N/A | 2026-05-26 | N/A | 2026-05-26 | N/A | 2026-05-26 | 2026-05-26 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | SARO NO. OSEC-3-26-01283 | 25000 | 25000 | 25000 | 25000 | 25000 | 25000 | N/A | N/A | 2026-05-26 | N/A | N/A | 2026-05-26 | 2026-06-01 | Completed
TRAININGS/SEMINARS | Procurement of Meals for thw Orientation on the Implementation of the Policy Guidelines of the BEIS for the Public Schools | PLANNING OFFICER III | No | Direct Acquisition | N/A | N/A | N/A | 2026-05-13 | N/A | 2026-05-13 | N/A | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | Division MOOE | 24800 | 24800 | 24800 | 24180 | 24180 | 24180 | N/A | N/A | 2026-05-13 | N/A | 2026-05-13 | N/A | 2026-05-14 | Completed
TRAININGS/SEMINARS | Procurement of Materials for the Printing of Grade 11 Numeracy and Literacy Assessment Tools | EPS | No | Direct Acquisition | N/A | N/A | N/A | 2026-05-19 | N/A | 2026-05-19 | N/A | 2026-05-19 | 2026-05-20 | 2026-03-06 | 2026-06-03 | 2026-06-03 | 2026-06-03 | DEPED-ROIII-2026-03-0104 | 152276.08 | 152276.08 | 152276.08 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | Completed
TRAININGS/SEMINARS | Procurement of Materials for the Division Training on Revised K to 12 Training for Grade 6, 9 and 10 teachers | SEPS | No | Direct Acquisition | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A |  | 0 |  |  | 0 |  |  | N/A | N/A |  | N/A | N/A | N/A |  | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Division Training on Enhancing Instructional Refinement in the Implementation of the Revised K to 12 Curriculum in Kindergarten | EPS | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A |  | 0 |  |  | 0 |  |  | N/A | N/A |  | N/A | N/A | N/A |  | Cancelled
TRAININGS/SEMINARS | Procurement of Materials for the Division Training on Enhancing Instructional Refinement in the Implementation of the Revised K to 12 Curriculum in Kindergarten | EPS | No | Small Value Procurement | N/A | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-05 | 2026-03-05 | 16-04-2026 | 16-4-2026 | 2026-04-16 | 2026-04-16 |  | 7500 |  |  | 0 |  |  | N/A | N/A |  | N/A | N/A | N/A |  | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Orientation on School Based Feeding Program for SY 2026-2027 | NURSE II - NIC | No | Small Value Procurement | N/A | N/A | N/A | 2026-05-26 | N/A | 2026-05-26 | N/A | 2026-05-26 | 2026-05-26 | 2026-06-03 | 2026-06-03 | 2026-06-05 | 2026-06-05 |  | 73000 | 73000 | 73000 | 73000 | 73000 | 73000 | N/A | N/A | 2026-05-26 | N/A | 2026-05-26 | N/A | 2026-06-05 | Completed
REPAIR AND MAINTENANCE | Freon Charging of CID Chief Aircon | AO IV-SUPPLY OFFICER | No | Direct Acquisition | N/A | N/A | N/A | 2026-05-25 | N/A | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 | 2026-06-05 | 2026-06-05 | 2026-06-22 | 2026-06-22 | Division MOOE | 5200 | 5200 | 52000 | 5200 | 5200 | 5200 | N/A | N/A | 2026-05-25 | N/A | 2026-05-25 | N/A | 2026-06-22 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Conduct of Division Rollout on Safer Learning Facilities (Pillar 1) and M7X School Ready Program June 16, 2026 | PDO II-DRRM | No | Small Value Procurement | N/A | N/A | N/A | 2026-06-01 | N/A | 2026-06-01 | N/A | 2026-06-01 | 2026-06-01 | 2026-06-16 | 2026-06-16 | 2026-06-16 | 2026-06-16 |  | 65000 | 65000 | 65000 | 65000 | 65000 | 65000 | N/A | N/A | 2026-06-01 | N/A | 2026-06-01 | N/A | 2026-06-16 | Completed
TRAININGS/SEMINARS | Procurement of Meals fo the Division Rolout on Plan Smart for Safe School June 24-26, 2026 | PDO II-DRRM | No | Small Value Procurement | N/A | N/A | N/A | 2026-05-29 | N/A | 2026-05-29 | N/A | 2026-06-01 | 2026-06-01 | 2026-06-24 | 2026-06-24 | 2026-06-24 | 2026-06-26 |  | 181500 | 181500 | 181500 | 179685 | 179685 | 179685 | N/A | N/A | 2026-05-29 | N/A | 2026-05-29 | N/A | 2026-06-26 | Completed
TRAININGS/SEMINARS | Procurement of Meals for the Review/Revisiting of Division Education Development Plan (DEDP) and Division FUnctional Divisions' Annual Implementation Plans (AIPs) June 24, 2026 | SEPS | No | Direct Acquisition | N/A | N/A | N/A | 2026-06-23 | N/A | N/A | N/A | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-23 | 2026-06-24 | 2026-06-24 | Division MOOE | 4800 | 4800 | 4800 | 4800 | 4800 | 4800 | N/A | N/A | 2026-06-23 | N/A | N/A | N/A | 2026-06-24 | Completed
TRAININGS/SEMINARS | Provision of Meals for the Conduct of the 2nd Public Expenditure and Institutional Review (PEIR) Mission Field Visit June 26, 2026 | AOV -ADMIN | No | Direct Acquisition | N/A | N/A | N/A | 2026-06-25 | N/A | N/A | N/A | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-26 | 2026-06-26 | Division MOOE | 6300 | 6300 | 6300 | 6300 | 6300 | 6300 | N/A | N/A | 2026-06-25 | N/A | N/A | N/A | 2026-06-26 | Completed
[18 empty] | Total Allotted Budget of Procurement Activities | 6206112.21 | 6196612.21 | 6243412.21
[18 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 5844989.71 | 5844989.71 | 5844489.71
[18 empty] | Total Savings (Total Allotted Budget - Total Contract Price) | 361122.5
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Notice of Award | Contract Signing | Notice to Proceed | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP)
ONGOING PROCUREMENT ACTIVITIES
TRAININGS/SEMINARS | Procurement of Meals for the Conductof FY 2026 SGOD PIR and Performance Evaluation (October 13, 2026) | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-01-21 | 2026-01-21 | 2026-02-18 | 2026-02-18 |  |  | Division MOOE | 12000 | 12000 | 12000 | 11850 | 11850 | 11850 | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Meals for the Conductof FY 2026 DIVISION PIR and Performance Evaluation (October 16, 2026) | SEPS-SMME | No | Small Value Procurement | N/A | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A | 2026-01-21 | 2026-01-21 | 2026-02-18 | 2026-02-18 |  |  | Division MOOE | 20000 | 20000 | 20000 | 19750 | 19750 | 19750 | N/A | N/A | 2026-01-21 | N/A | 2026-01-21 | N/A |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Meals for the Coonduct of Capacity-Building on Research on: Maximixing Research Results for School and Division Improvement September 24-25, 2026 | SEPS-PAR | No | Small Value Procurement | N/A | N/A | N/A | 2026-02-12 | N/A | 2026-02-12 | N/A | 2026-02-12 | 2026-02-12 |  |  |  |  | Division MOOE | 59000 | 59000 | 59000 | 57820 | 57820 | 57820 | N/A | N/A | 2026-02-12 | N/A | 2026-02-12 | N/A |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Procurement of Micro SD Card with Adapter for the Project Listen 4.0 | EPSvr-LRMDS | No | Small Value Procurement | N/A | N/A | N/A | 2026-06-16 | N/A | 2026-06-16 | N/A | 2026-06-16 | 2026-06-16 |  |  |  |  | Division MOOE | 5000 | 5000 | 5000 | 3900 | 3900 | 3900 | N/A | N/A | 2026-06-16 | N/A | 2026-06-16 | N/A |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Procurement of Tablet-Assisted Customer Satisfaction Survey System for Improved Clinet Feedback Collection | AOV -ADMIN | No | Small Value Procurement | N/A | N/A | N/A | 2026-06-16 | N/A | 2026-06-16 | N/A | 2026-06-16 | 2026-06-16 |  |  |  |  | Division MOOE | 225000 | 225000 | 225000 | 222000 | 222000 | 222000 | N/A | N/A | 2026-06-16 | N/A | 2026-06-16 | N/A |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Purchase of Toner for HR Office Copiers | SUPPLY OFFICER | No | Direct Acquisition | N/A | N/A | N/A | 2026-03-13 | N/A | 2026-03-13 | N/A | 2026-03-13 | 2026-03-13 | 2026-06-25 | 2026-06-25 |  |  | Division MOOE | 10480 | 10480 | 10480 | 10480 | 10480 | 10480 | N/A | N/A | 2026-03-13 | N/A | 2026-03-13 | N/A |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Provision of Additional Water Tank to supply the OSDS, SGOD, and CID Buildings | AOV -ADMIN | No | Small Value Procurement | N/A | N/A | N/A | 2026-04-06 | N/A | 2026-04-06 | N/A | 2026-04-06 | 2026-04-06 | 2026-06-18 | 2026-06-18 |  |  | Division MOOE | 170000 | 170000 | 170000 | 167000 | 167000 | 167000 | N/A | N/A | 2026-04-06 | N/A | 2026-04-06 | N/A |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Procurement of Materials for the 2026 Regional Festival of Talents (RFOT) Delegation of the Schools Division of Angeles City | EPS | No | Direct Acquisiton | N/A | N/A | N/A | 2026-06-16 | N/A | 2026-06-16 | N/A | 2026-06-16 | 2026-06-16 |  |  |  |  | DEFED-ROIII-2026-03-0079 | 1250 | 1250 | 1250 | 1250 | 1250 | 1250 | N/A | N/A | 2026-06-16 | N/A | 2026-06-16 | N/A |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Meals for Conduct of Human Resource Training for the Schools Leaders and Teachers for FY 2026 | SEPS | No | Competitive Bidding | 2026-04-28: 2026-03-26; 2026-05-05: 2026-04-06; 2026-05-20: 2026-04-20; 2026-05-20: 2026-04-20 |  | 2602000 | 2602000 | 2602000 | 0 | 0 | 0 | N/A | 2026-04-06 | 2026-04-20 | 2026-04-20 | 2026-04-20 |  |  | Failed due to disqualification of bidder's of NFCC
TRAININGS/SEMINARS | Procurement of Meals for Conduct of Human Resource Training for the Schools Leaders and Teachers for FY 2026 | SEPS | No | Negotiated Procurement | [14 empty] | 2602000 | 2602000 | 2602000 | 2602000 | 2602000 | 2602000 | N/A | [6 empty] | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Procurement of Supplementary Learning Resoruces for School Libraries Lot 12 | EPSvr-LRMDS | No | Direct Contracting | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED-ROIII-2025-06-1227 SUB-ARO | 16860 | 16860 | 16860 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Procurement of Supplementary Learning Resoruces for School Libraries Lot 15 | EPSvr-LRMDS | No | Direct Contracting | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED-ROIII-2025-06-1227 SUB-ARO | 83520 | 83520 | 83520 | 0 | 0 | 0 | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Procurement of Supplementary Learning Resoruces for School Libraries Lot 18 | EPSvr-LRMDS | No | Direct Contracting | N/A | N/A | N/A | 2026-05-25 | N/A | 2026-05-25 | N/A | 2026-05-25 | 2026-05-25 |  |  |  |  | DEPED-ROIII-2025-06-1227 SUB-ARO | 37960 | 37960 | 37960 | 37960 | 37960 | 37960 | N/A | N/A | 2026-05-25 | N/A | 2026-05-25 | N/A |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Meals for the Conduct of Capacity Building on Social Well-being and Workplace Relationship for SDO Angeles City Administrative Personnel | AOV -ADMIN | No | Direct Acquisition | N/A | N/A | N/A | 2026-05-13 | N/A | 2026-05-13 | N/A | 2026-05-13 | 2026-05-13 | 2026-05-14 | 2026-05-14 | 2026-05-18 | 2026-05-19 | Division MOOE | 164800 | 164800 | 164800 | 164800 | 164800 | 164800 | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-19 | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Plaque for the Conduct of 2026 Division Project ROSES (Recognition of Outstanding Stakeholders for Engagement asnd Support for Basic Education) July 30, 2026 | EPS II/SEPS | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A |  | 30000 | 30000 | 30000 | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Meals for the Conduct of 2026 Division Project ROSES (Recognition of Outstanding Stakeholders for Engagement asnd Support for Basic Education) July 30, 2026 | EPS II/SEPS | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A |  | 30000 | 30000 | 30000 | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Printer for the Division Training on Revised K to 12 Training for Grade 6, 9 and 10 teachers | SEPS | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A |  | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Procurement of Printing and Delivery of Reading Materials for Key Stage 1 | SEPSvr-LRMDS | No | Competitive Bidding | 2026-04-23: 2026-06-01; 2026-04-28: 2026-06-11; 2026-05-05: 2026-06-18; 2026-05-20: 2026-06-30; 2026-05-20: 2026-06-30; 2026-05-20: 2026-06-30; 2026-05-21: 2026-07-01 |  | 4595100 | 4595100 | 4595100 | 0 | [9 empty] | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Meals for the Division Seminar-Workshop on School Climate Action Plan | PDO II-DRRM | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-21: N/A |  | 0 |  |  | 0 |  |  | N/A | N/A |  | N/A |  | N/A |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Meals for the Division Rollout on DRR Integrated Learning Guide | PDO II-DRRM | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-21: N/A |  | 0 |  |  | 0 |  |  | N/A | N/A |  | N/A |  | N/A |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Procurement of Laptop and Inks for Efficient Data Management, Monitoring, and Reporting of the Implementation of School Based Feeding Program (SBFP) | NURSE II - NIC | No | Direct Acquisition | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: 2026-06-19; 2026-05-20: N/A; 2026-05-20: 2026-06-19; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 103200 | 103200 | 103200 | 0 |  |  | N/A | N/A |  | N/A |  | N/A |  | Ongoing Procurement Process
REPAIR AND MAINTENANCE | Repair of Various Comfort Rooms in the Schools Division Office | AO V | No | Direct Acquisition | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
REPAIR AND MAINTENANCE | Servicing and Maintenance of Innova (SJS 422) | AO IV-SUPPLY OFFICER | No | Direct Contracting | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
REPAIR AND MAINTENANCE | Aircon Servicing of SDS Service Vehicle (Strada Pickup) | AO IV-SUPPLY OFFICER | No | Direct Contracting | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Implementation of SBFP - Procurement of IEC Materials (Plaque) | NURSE II - NIC | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Implementation of SBFP - Procurement of IEC Materials (Tarpaulin) | NURSE II - NIC | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Implementation of SBFP - Procurement of gardening materials | NURSE II - NIC | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Implementation of SBFP - Procurement of medicines | NURSE II - NIC | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Implementation of SBFP - Procurement of Meals Program Implementation Review | NURSE II - NIC | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Implementation of SBFP - Nutritious Food Product | NURSE II - NIC | No | Competitive Bidding | 2026-04-23: 2026-06-11; 2026-04-28: 2026-06-24; 2026-05-05: 2026-06-30; 2026-05-20: 2026-07-13; 2026-05-20: 2026-07-13; 2026-05-20: 2026-07-13; 2026-05-21: 2026-03-14 | DEPED ROIII 2024-03-0230 | 34842720 | 34842720 | 34842720 | 0 | [9 empty] | Ongoing Procurement Process
TRAININGS/SEMINARS | Implementation of SBFP - Procurement of Meals Mid-Implementation Review | NURSE II - NIC | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Implementation of SBFP - Procurement of Meals Mid-Implementation Review | NURSE II - NIC | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2024-03-0230 | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Procurement of SAFER Bag | PDO II-DRRM | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: 2026-06-18; 2026-05-20: N/A; 2026-05-20: 2026-06-18; 2026-05-21: N/A | SARO OSEC 3-26-01520 | 232000 | 232000 | 232000 | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
REPAIR AND MAINTENANCE | Leak Test and Freon Charging of Accounting Office Window Type Aircon | AO IV-SUPPLY OFFICER | No | Direct Acquisition | N/A | N/A | N/A | 2026-06-09 | N/A | 2026-06-09 | N/A | 2026-06-09 | 2026-06-09 |  |  |  |  | Division MOOE | 4100 | 4100 | 4100 | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Meals for the Synergizing Resources: Building Effective Partnerships for Basic Education September 3, 2026 | EPS II/SEPS | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A |  | 0 |  |  | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Materials for the Division Training Workshop on Innovative & Learner-Centered Pedagogies for Elementary Science Teachers | EPS | No | Direct Acquisition | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | HRTD FUNDS | 4500 | 4500 | 4500 | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Materials for the 2026 Alternative Learning System End-of-School Year (EOSY) Rites | EPS | No | Direct Acquisition | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | DEPED ROIII 2026-04-0464 | 11524 | 11524 | 11524 | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
TRAININGS/SEMINARS | Procurement of Meals for the Division Seminar-Workshop on the Reconciliation and Consolidation of CY 2026 Mid-Year Financial Reports | AO V | No | Direct Acquisition | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | Division MOOE | 10000 | 10000 | 10000 | 0 |  |  |  |  | N/A |  | N/A |  |  | Ongoing Procurement Process
SUPPLIES AND MATERIALS | Provision of Necessary Supplies for FY 2026 in the Payroll Services Unit | AO IV | No | Small Value Procurement | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | Division MOOE | 170000 | 170000 | 170000 | 0 | [9 empty] | Ongoing Procurement Process
REPAIR AND MAINTENANCE | Termite Treatment for the Gabaldon Building | AOV -ADMIN | No | Direct Acquisition | 2026-04-23: N/A; 2026-04-28: N/A; 2026-05-05: N/A; 2026-05-20: N/A; 2026-05-20: N/A; 2026-05-21: N/A | Division MOOE | 57000 | 57000 | 57000 | 0 | [9 empty] | Ongoing Procurement Process
TRAININGS/SEMINARS | Provision of Meals for the Conduct of the 2nd Public Expenditure and Institutional Review (PEIR) Mission Field Visit June 26, 2026 | AOV -ADMIN | No | Direct Acquisition | N/A | N/A | N/A | 2026-06-25 | N/A | N/A | N/A | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-25 | 2026-06-26 | 2026-06-26 | Division MOOE | 6300 | 6300 | 6300 | 6300 | 6300 | 6300 | N/A | N/A | 2026-06-25 | N/A | N/A | N/A | 2026-06-26 | Ongoing Procurement Process
[18 empty] | Total Allotted Budget of On-going Procurement Activities | 46106314 | 46106314 | 46106314 | 3305110 | 3305110 | 3305110
| Prepared by: |  |  |  | 2026-04-23: Reviewed by:; 2026-05-20: Recommended for Approval by: |  |  |  |  | APPROVED:
| MARJORIE M. GUIAO RPm |  |  |  | 2026-04-23: ENGR. MARIA CRISTINA S. SARMIENTO; 2026-05-20: EDGAR L. MANABAT PhD |  |  |  |  | ENGR. EDGARD C. DOMINGO PhD, CESO V
| BAC Secretariat Member |  |  |  | 2026-04-23: BAC Secretariat Head; 2026-05-20: SGOD Chief/BAC Chairperson |  |  |  |  | Schools Division Superintedent

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds | Mode of Procurement
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget) | Competitive Bidding
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget) | Limited Source Bidding
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget) | Direct Contracting
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution | Repeat Order
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution | Shopping 52.1(a) - Unforeseen Contingency
Failed under Section 35.1 (b) |  | BAC Resolution |  | Shopping 52.1(b) - Regular Office Supplies and Equipment not available in PS
Failed under Section 35.1 (c) |  | Award |  | Negotiated Procurement - Two Failed Biddings
Failed under Section 41 (b) |  | Cancelled |  | Negotiated Procurement - Emergency Cases
Failed under Section 41 (c) |  |  |  | Negotiated Procurement - Take-Over of Contracts
Contract was extended |  |  |  | Negotiated Procurement - Adjacent or Contiguous
Contract was renewed |  |  |  | Negotiated Procurement - Agency-to-Agency
Cancelled |  |  |  | Negotiated Procurement - Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services
Others, please encode directly on the cell |  |  |  | Negotiated Procurement - Highly Technical Consultants
Negotiated Procurement - Defense Cooperation Agreement
Negotiated Procurement - Small Value Procurement
Negotiated Procurement - Lease of Real Property and Venue
Negotiated Procurement - NGO Participation
Negotiated Procurement - Community Participation
Negotiated Procurement - UN Agencies, Int'l Organizations or International Financing Institutions
Negotiated Procurement - Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant Products, Electronic Charging Devices, and Online Subscriptions
Foreign Guidelines - Competitive Bidding
Foreign Guidelines - Alternative Method
Competitive Dialogue
Unsolicited Offer with Bid Matching
Direct Acquisition
Direct Sales
Direct Procurement for Science, Technology, and Innovation
Others, specify in the remarks: Mode of Procurement use <Mode>